## 1. Access
2015-16 Goals, Activities, Funding, and Evaluation
Indicator A.1 |  | Access
Indicator Goal |  | To improve enrollment access for Latino/a students who experience disproportionate impact
Target Populations |  | Latino/a
Gap, Year |  | 80% index = 0.49, 2012-13 |  | (23.1% at De Anza College vs. 25.6% within Santa Clara Co.)
Target Population Goal |  | No gap, proportion of Latino/a at De Anza College will be ≥ to the County
Target Goal Year |  | 2020
DIRECTIONS: Describe the activity. If it is a new intervention, include references to any literature or research demonstrating its effectiveness. Include start and end dates for the activity, and the budget allocated to the activity, including—student equity and other funding**). If augmenting an existing program or activity, provide an overview of program history, date of implementation, relevant data on impact from research and evaluation, timeline and description of activity to be implemented with student equity funding, and budget including expenditures of student equity funding and other program funding**, including a description of how student equity funds will not be supplanting other district funds. Planned expenditures should be listed here as well as in the Student Equity Plan Summary Budget spreadsheet.
*Activity Type reflects state-provided categories and are coded as follows: (1) curriculum/course development or adaptation, (2) direct student support, (3) instructional support activities, (4) outreach, (5) professional development, (6) research and evaluation, (7) student equity coordination/planning, and (8) student services or other categorical program.
ID | Activity Type* | Target Group | # Students Affected | Start | End | Responsible Person/Team Lead | SAMPLE (for internal discussion purposes only) | Equity Funds | Other Funds
A.1.1 | 4, 8, 6 | High school counselors | TBD [need average attendance] | TBD | Event on 10/30/15 | TBD | Activity Implementation Plan: High School Partners Appreciation Breakfast & Annual Update (Outreach) The outreach and counseling team will discuss the following at the annual High School Partners Appreciation Breakfast & Annual Update (October 30, 2015) event: 1. De Anza is an AAPI serving institution and is about to become a Hispanic-serving institution; 2. De Anza has established instruction/student services programs to serve its growing Latino/a student population; (Summer Bridge, First Year Experience (FYE), Latino/a Empowerment at De Anza (LEAD), and Puente Project) 3. De Anza is hosting two Latino/a Student Conference (March and April 2016) for high school students (conference objectives: meet faculty and faculty, discover value in participating in student services programs and campus activities) How does the activity link to the indicator goal? The outreach will provide an opportunity for De Anza to build rapport with high school counselors and inform them about the students services programs that helps direct and engage students to be successful at De Anza. The call-to-action from this outreach event is to have the influencers return to their respective high schools and recommend De Anza to their Latino/a students, and to encourage these students to attend the Latino/a Student Conference. What are the activity's metric/goal/evaluation? The student equity research analyst will develop an exit survey to obtain attendees’ feedback, which will be used to improve future High School Partners Appreciation Breakfast & Annual Update events. The survey will be administered one time and the findings will be shared with outreach, counseling, and Equity/3SP advisory committee members. The goal from this outreach is to increase the number of high school counselors engaged [insert goal]. The outreach team will track the number of counselors in attendance.
A.1.2 | 4, 8, 6 | Prospective Latino/a students | TBD [need average attendance] | TBD | March and April 2016 | TBD | Activity Implementation Plan: Latino/a Student Conference (Outreach) The outreach and counseling team will follow-up with their high school contacts (counselors, administrators, teachers) and invite Latino/a high school students to the annual Latino/a Student Conference (March and April 2016) at De Anza. How does the activity link to the indicator goal? The outreach event will provide Latino/a high school students the opportunity to meet faculty and staff, discover value in student services programs and campus activities, experience initial college campus environment, and receive guidance on college application, financial aid, assessment testing, and registration. What are the activity's metric/goal/evaluation? The student equity research analyst will develop an exit survey to obtain attendees’ feedback, which will be used to improve future Latino/a Student Conferences and improve outreach communication/messaging to Latino/a students. The survey will be administered one time and the findings will be shared with outreach, counseling, and equity advisory committee members. The goal from this outreach event is to increase the number of Latino/a high school student engaged [insert goal]. The outreach team will track the number of prospective Latino/a students, and follow-up with attendees to complete their application and assessment test. | 0 | 0
A.1.3 | 2, 4, 6 | 2, 4, 6 | Prospective and Current Latino/a students | TBD | January 2016 | December 2016 | Activity Implementation Plan: Permanent Signage and Spanish, Tagalog, and Vietnamese Translation (Marketing/Communications) A number of student services departments recently relocated offices at De Anza. The college operations/marketing and communications team will develop [X] permanent signage for the Administration and Student & Community Services buildings to direct students to the appropriate service areas such as admissions and records, financial aid, counseling, student success and retention services. Signage will be in English, Spanish, and [X] to reflect the predominate languages spoken on campus. Additionally, there will be Spanish, Tagalog and Vietnamese translations of college website information. How does the activity link to the indicator goal? The activity will provide and reinforce De Anza’s welcoming and inclusive campus climate, and will help direct students to the appropriate service areas. What are the activity's metric/goal/evaluation? Evaluation of the permanent signage will be incorporated in the Community College Survey of Student Engagement (CCSSE) and individual student services program review. The CCSSE is administered one time during the spring quarter, and program reviews are completed by [X]. The institutional research team will analyze and share the CCSSE survey results with the college. | 0 | 0
A.1.4 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Director of Student Success and Retention Services The Academic Services division will hire (1) Director of Student Success and Retention Services to coordinate and expand Summer Bridge, First Year Experience, Puente Project, and Umoja program within the context of SSSP and Student Equity initiatives. The Director will collaborate with SSRS counselors/coordinators, Learning in Communities, Student Success Center, and Instructional departments to track students' course and degree/certification completion. How does the activity link to the indicator goal? The Director of Student Success and Retention Services will be additional support team member to assist with student success and equity initiatives. What are the activity's metric/goal/evaluation? Each learning community program will track the number of African American, Filipino, and Latino/a students it will serve in 2015-16 and their associated course and degree/certification completion rates, and provide reporting in their annual program review. The student equity research analyst will analyze course and degree/certification completion for the state-mandated Equity Plan and Scorecard submissions. | 0 | 0
A.1.5 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: How does the activity link to the indicator goal? What are the activity's metric/goal/evaluation? | 0 | 0
A.1.6 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: How does the activity link to the indicator goal? What are the activity's metric/goal/evaluation? | 0 | 0
A.1.7 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: How does the activity link to the indicator goal? What are the activity's metric/goal/evaluation? | 0 | 0
5
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS

## 1. Access-Financial Aid
2015-16 Goals, Activities, Funding, and Evaluation
Indicator A.2 |  | Financial Aid
Indicator Goal |  | To improve financial aid access for Filipino students who experience disproportionate impact
Target Populations |  | Filipino
Gap, Year |  | 80% index = 0.62, 2012-13 |  | (Filipinos account for 6.2% of students and 6.6% of those receiving financial aid)
Target Population Goal |  | [TBD # or %] Filipino students will receive financial aid
Target Goal Year |  | 2020
DIRECTIONS: Describe the activity. If it is a new intervention, include references to any literature or research demonstrating its effectiveness. Include start and end dates for the activity, and the budget allocated to the activity, including—student equity and other funding**). If augmenting an existing program or activity, provide an overview of program history, date of implementation, relevant data on impact from research and evaluation, timeline and description of activity to be implemented with student equity funding, and budget including expenditures of student equity funding and other program funding**, including a description of how student equity funds will not be supplanting other district funds. Planned expenditures should be listed here as well as in the Student Equity Plan Summary Budget spreadsheet.
*Activity Type reflects state-provided categories and are coded as follows: (1) curriculum/course development or adaptation, (2) direct student support, (3) instructional support activities, (4) outreach, (5) professional development, (6) research and evaluation, (7) student equity coordination/planning, and (8) student services or other categorical program.
ID | Activity Type* | Target Group | # Students Affected | Start | End | Responsible Person/Team Lead | SAMPLE (for internal discussion purposes only) | Equity Funds | Other Funds
A.2.1 | 2, 4, 6, 8 | Prospective Filipino students | TBD [need average attendance] | TBD | Event on 4/27/16 | TBD | Activity Implementation Plan: General and Filipino/Southeast Asian Student Conference (Outreach) Financial aid and EOPS advisors, in collaboration with the outreach team, will inform and guide prospective students how to apply for financial aid (grants, scholarships, waivers, and loans) and EOPS at the annual Filipino/Southeast Asian Student Conference on April 27, 2016. How does the activity link to the indicator goal? The outreach event will provide prospective Filipino students hands-on support to apply for financial aid/assistance. What are the activity's metric/goal/evaluation? The student equity research analyst will develop an exit survey to obtain attendees’ feedback, which will be used to help improve future Filipino/ Southeast Asian Student Conferences and outreach communication/messaging to Filipino students. The survey will be administered one time and the findings will be shared with outreach, counseling, financial aid, EOPS, and Equity/3SP advisory committee members. The goal from this outreach event is to: 1. Increase Filipino high school students attendance [insert goal]. The outreach team will track the number of students in attendance and follow-up with at least [insert goal] attendees to make sure they have completed their application and assessment test. 2. Increase the number of Filipino students who apply for financial aid/assistance. Financial aid and EOPS teams will follow-up with attendees, and track the number of Filipino students they will serve 2015-16 [insert goal]. | 0 | 0
A.2.2 | TBD | TBD | TBD | TBD | TBD | TBD | What is the activity implementation plan? How does the activity link to the indicator goal? What are the activity's metric/goal/evaluation? | 0 | 0
A.2.3 | TBD | TBD | TBD | TBD | TBD | TBD | What is the activity implementation plan? How does the activity link to the indicator goal? What are the activity's metric/goal/evaluation? | 0 | 0
DRAFT - WORK IN PROGRESS

## 2. Course Completion
2015-16 Goals, Activities, Funding, and Evaluation
Indicator B.1 |  | Course Completion
Indicator Goal |  | To improve course completion rates for African American and Latino/a students
Target Populations |  | African American |  |  |  | Latino/a
Gap, Year |  | proportionality index = 0.83, 2012-13 |  |  |  | proportionality index = 0.88, 2012-13
Target Population Goal |  | Course completion proportionality index for African American and Latino/a students will each be ≥ 0.90
Target Goal Year |  | 2020
Indicator B.2 |  | Academic Probation
Goal |  | To decrease academic probation rates for students who experience disproportionate impact
Target Populations |  | African American |  |  |  | Latino/a
Gap, Year |  | proportionality index = 1.59, 2012-13 |  |  |  | proportionality index = 1.74, 2012-13
Goal |  | Academic probation rates will decrease by 1%, bringing proportionality indexes for African American students to ≤ 1.50 and for Latino/a students to ≤ 1.70
Target Goal Year |  | 2020
DIRECTIONS: Describe the activity. If it is a new intervention, include references to any literature or research demonstrating its effectiveness. Include start and end dates for the activity, and the budget allocated to the activity, including—student equity and other funding**). If augmenting an existing program or activity, provide an overview of program history, date of implementation, relevant data on impact from research and evaluation, timeline and description of activity to be implemented with student equity funding, and budget including expenditures of student equity funding and other program funding**, including a description of how student equity funds will not be supplanting other district funds. Planned expenditures should be listed here as well as in the Student Equity Plan Summary Budget spreadsheet.
*Activity Type reflects state-provided categories and are coded as follows: (1) curriculum/course development or adaptation, (2) direct student support, (3) instructional support activities, (4) outreach, (5) professional development, (6) research and evaluation, (7) student equity coordination/planning, and (8) student services or other categorical program.
Note: Increasing completion rates and combatting academic probation rates go hand-in-hand; and therefore, the following activities are planned to simultaneously address the aforementioned goals.
ID | Activity Type* | Target Group | # Students Affected | Start | End | Responsible Person/Team Lead | SAMPLE (for internal discussion purposes only) | Equity Funds | Other Funds
B.1.1 and B.2.1 | 1, 2, 6, 8 | African American and Latino/a students | AA - 50 Latino/a - 300 | September 2015 | June 2016 | TBD | Activity Implementation Plan: New Student Success and Retention Services Counselor (dedicated to African American and Latino/a students) De Anza will hire a new counselor to specifically assist African American and Latino/a students with their course planning, and be a point-of-contact to facilitate academic probation interventions, including: 1. encouraging students to participate in learning communities (Summer Bridge, FYE, LEAD, MPS, Puente Project, Umoja Program) 2. facilitating students' academic progress, participation in learning communities, and attendance at tutoring sessions 3. coordinating the development of a new UMOJA learning community that is aligned with the Statewide UMOJA Consortium efforts. How does the activity link to the indicator goal? The new counselor will build rapport and provide guidance to primarily African American and Latino/a students in order to help them stay focused and engaged with their educational goals. What are the activity's metric/goal/evaluation? The new counselor will strive to see at least 5% of the African American (50) and 2% Latino/a (120) student population for 2015-16. The SSRS program review will track the number of African American and Latino/a students it will serve. The student equity research analyst will analyze course completion rates at the end of quarter term and annually for state-mandated Equity Plan and Scorecard submissions. | 0 | 0
B.1.2 and B.2.2 | 6, 8 | African American and Latino/a students | TBD | April 2016 | June 2016 | TBD | Activity Implementation Plan: Multiple Measures Assessment Project (Pilot) De Anza College is one of 27 pilot colleges participating in the Multiple Measures Assessment Project (MMAP) as part of the Common Assessment Initiative (CAI). The MMAP project asks pilot colleges to analyze a retrospective cohort of students using the multiple measures rule sets, which uses high school courses, grades and overall GPA to predict students’ placement in college-level math and English courses. The rule set, or model, places students in a math and English course where their predicted success rate will be at least a 2.2 GPA. As part of the pilot project, De Anza will use the multiple measures model to place a cohort of students in spring 2016, and to implement 1 of 6 recommended Non-Cognitive Variable (NCV) scales to a cohort of students and report the responses to Cal-PASS Plus at the end of spring 2016. The data will be used to determine the value added of incorporating the NCV to the multiple measures model. At the conclusion of the pilot, Cal-Pass Plus will provide college-level analysis to the pilot colleges and report its findings to the state. How does the activity link to the indicator goal? The activity could effectively place students in a higher math and/or English level; and therefore, saving students time and increasing their likelihood of throughput. In addition, the activity will enable De Anza to evaluate the effectiveness of its current placement process and the use of high school transcript data to predict math and English course placement. What are the activity's metric/goal/evaluation? The institutional research team will analyze and share results of the pilot outcomes to the college. Pending the pilot project’s final outcomes, De Anza will consider potential revisions to its assessment testing. | 0 | 0
B.1.3 and B.2.3 | 1, 2, 8 | African American and Latino/a students | TBD | September 2015 | December 2016 | TBD | Activity Implementation Plan: Expanding Learning Communities/Curricular Pathways The learning communities that generally have high participation from African American and Latino/a students include: First Year Experience (FYE), Latino/a Empowerment at De Anza (LEAD), Learning in Community (LinC), Puente Project, and Umoja Program. A new curricular pathway will be implemented to serve Student Athletes of Color, combining developmental Reading, English, Academic Support, Counseling, and Humanities (REACH). Counselors from each program will work with the newly hired counselor dedicated to African American and Latino/a students (see Activity B.1.1). How does the activity link to the indicator goal? Participation and retention in the aforementioned programs will assist African American and Latino/a students stay on track as each of the program have built-in support from peer students and a dedicated counselor. What are the activity's metric/goal/evaluation? Learning communities will retain [X%] of its students. Each student success and retention program will track the number of African American and Latino/a students it will serve 2015-16 and provide reporting in their annual program review.
B.1.4 and B.2.4 | 1, 2, 8 | African American and Latino/a students | TBD | September 2015 | December 2016 | TBD | Activity Implementation Plan: Peer Mentoring Coordinator The Academic Services Division and Office of Instruction will hire a Faculty Peer Coordinator to develop a campus-wide Peer Mentoring Program. Services to students and faculty include: • culturally responsive peer mentor training for students and faculty • course assigned peer mentors for areas in which student services has been limited; for example, Auto Tech, Biology, Business, Computer Science, etc. • peer support in navigating college life • leadership development and skills training in working with campus and external partners How does the activity link to the indicator goal? Participation and retention in the aforementioned program will assist African American and Latino/a students stay on track as each of the program have built-in support from peer mentors. What are the activity's metric/goal/evaluation? The program coordinator will track the number of African American and Latino/a students and Faculty it will serve 2015-16 and provide reporting in their annual program review. | 0 | 0
B.1.5 and B.2.5 | 5 | Faculty and Staff | TBD | September 2015 | December 2016 | TBD | Activity Implementation Plan: Teaching Men of Color in Community College (Certification) Faculty, administrators, and staff will participate in an online certification in Teaching Men of Color in Community College. The one-week certification is offered through San Diego State University, and aims to enhance the preparedness of instructional faculty in the community college to facilitate teaching and learning among college men of color. The certification program consists of the following five modules: • Day 1 – Factors necessitating enhanced teaching and learning strategies for men of color • Day 2 – Theoretical and epistemological foundations for teaching men of color • Day 3 – Building relationships with college men of color (live session @ 4pm PST) • Day 4 – Teaching and learning strategies for instructional faculty • Day 5 – *Virtual discussion* (live session @ 4pm PST) What are the activity's metric/goal/evaluation? The activity will provide faculty and staff with additional tools to improve pedagogies and student rapport. What are the activity's metric/goal/evaluation? There will be [15] faculty and staff who will enroll in the Teaching Men of Color in Community College certification. These participants will incorporate their learnings in their respective areas: classroom, student services, and program reviews. | 0 | 0
B.1.6 and B.2.6 | 6 | TBD | TBD | September 2015 | June 2016 | L. Ly | Activity Implementation Plan: Student Equity Research Analyst The Office of Instruction has hired a research analyst to support state-mandated equity reporting. In addition, the research analyst is building rapport and working with various college areas and programs to communicate the equity analysis and help embed evaluation/metrics into program activities that support and enhances equity initiatives. How does the activity link to the indicator goal? The research analyst is communicating equity findings on the equity plan target groups: African Americans, Filipinos, Latino/a, disabled, foster youth, low income, and veterans. What are the activity's metric/goal/evaluation? The research analyst provides equity data analysis during spring and fall quarters when the Equity Plan is undergoing planning and reporting to the governance groups. In addition, the research analyst provides ad hoc equity analysis as needed. | 0 | 0
B.1.7 and B.2.7 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Director of Student Success and Retention Services The Academic Services division will hire (1) Director of Student Success and Retention Services to coordinate and expand Summer Bridge, First Year Experience, Puente Project, and Umoja program within the context of SSSP and Student Equity initiatives. The Director will collaborate with SSRS counselors/coordinators, Learning in Communities, Student Success Center, and Instructional departments to track students' course and degree/certification completion. How does the activity link to the indicator goal? The Director of Student Success and Retention Services will be additional support team member to assist with student success and equity initiatives. What are the activity's metric/goal/evaluation? Each learning community program will track the number of African American, Filipino, and Latino/a students it will serve in 2015-16 and their associated course and degree/certification completion rates, and provide reporting in their annual program review. The student equity research analyst will analyze course and degree/certification completion for the state-mandated Equity Plan and Scorecard submissions. | 0 | 0
B.1.8 and B.2.8 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Director of STEM Pathways The Physical Sciences, Mathematics, and Engineering Division will hire [1] Director of STEM Pathways to coordinate the Statway and Math Performance and Success programs to ensure access and quality instruction for African American, Filipino, and Latino/a students. The Director will develop campus partnerships with SSRS programs, Learning in Communities, Outreach and Relations with Schools, Business/Computer Science, and Biological and Health Sciences. How does the activity link to the indicator goal? The Director of STEM Pathways will be additional support team members to assist with student success and equity initiatives. What are the activity's metric/goal/evaluation? The Director of STEM Pathways will track the number of African American, Filipino, and Latino/a students it will serve in 2015-16 and their associated course and degree/certification completion rates, and provide reporting in their annual program review. The student equity research analyst will analyze course and degree/certification completion for the state-mandated Equity Plan and Scorecard submissions. | 0 | 0
B.1.9 and B.2.9 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Student Equity Initiatives Program Coordinator II The Office of Equity, Social Justice, and Multicultural Education will hire a program coordinator II to support the college's student equity planning initiatives and activities. The equity program coordinator will assist with creating linkages among student success programs, professional development trainings, and overall strategic planning and implementation. How does the activity link to the indicator goal? The program coordinator II will work specifically with students, faculty, and classified professional on strategies for apply our conceptual framework, campus-wide collaborations, and high impact practices that could be utilized to support our identified target populations. What are the activity's metric/goal/evaluation? The program coordinator II will assist with the delivery of professional development trainings and programs as well as provide coaching as needed; and the student equity research analyst will analyze and compare the impact on the select indicators as they correspond with the identified trainings/programs/coaching per the rates of faculty participating in these trainings to those not able to participate. The goal is to have identified indicators impacted per the rates of faculty participating in equity and cultural responsiveness professional development trainings be higher than their counterpart. | 0 | 0
B.1.10 and B.2.10 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Office of Equity Administrative Assistant The Office of Equity, Social Justice, and Multicultural Education will hire a half-time administrative assistant to support the equity office and staff development office in meeting the college's equity planning goals and activities. The equity administrative assistant will specifically assist with budget tracking, record keeping, contracting, conference/training/workshop logistics, scheduling, and related office administration. The administrative assistant will also support linkages between the equity office and staff development, which includes assisting with Partners In Learning, Service Excellence, and related equity programs that emphasize supporting classified professionals in creating a welcoming environment for students and identifying linkages to the indicators. How does the activity link to the indicator goal? The program administrative assistant will work specifically with the equity office as well as those accessing services from these campus-wide offices. What are the activity's metric/goal/evaluation? The program assistant will assist with all related equity programming and services related to the state equity report initiatives; and the student equity research analyst will analyze and compare the impact on the select indicators as they correspond with the identified trainings/programs/coaching per the rates of faculty participating in these trainings to those not able to participate. The goal is to have identified indicators impacted per the rates of faculty participating in equity and cultural responsiveness professional development trainings be higher than their counterpart. | 0 | 0
B.1.11 and B.2.11 | TBD | TBD | TBD | TBD | TBD | TBD |  | 0 | 0
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS

## 3¦4. ESL & Basic Skills
2015-16 Goals, Activities, Funding, and Evaluation
Indicator C.1 |  | ESL Completion
Indicator Goal |  | To improve ESL completion rates for African American and Latino/a students who experience disproportionate impact
Target Populations |  | African American |  |  | Latino/a
Gap, Year |  | 80% index = 0.78, 2012-13 |  |  | 80% index = 0.18, 2012-13
Target Population Goal |  | ESL completion rates for African American students will be ≥ 60.0% (currently 58.0%) and for Latino/a students will be ≥ 15.0% (currently 13.0%)
Target Goal Year |  | 2020
Indicator C.2 |  | English Basic Skills
Indicator Goal |  | To improve English basic skills completion rates for African American and Latino/a students who experience disproportionate impact
Target Populations |  | African American |  |  | Latino/a
Gap, Year |  | 80% index = 0.76, 2012-13 |  |  | 80% index = 0.64, 2012-13
Target Population Goal |  | English basic skills completion rates for African American students will be ≥ 6.5% (currently 4.5%) and for Latino/a students will be ≥ 20.0% (currently 18.0%)
Target Goal Year |  | 2020
Indicator C.3 |  | Math Basic Skills
Indicator Goal |  | To improve Math basic skills completion rates for African American and Latino/a students who experience disproportionate impact
Target Populations |  | African American |  |  | Latino/a
Gap, Year |  | 80% index = 0.60, 2012-13 |  |  | 80% index = 0.63, 2012-13
Target Population Goal |  | Math basic skills completion rates for African American students will be ≥ 65.0% (currently 63.0%) and for Latino/a students will be ≥ 55.0% (currently 53.0%)
Target Goal Year |  | 2020
DIRECTIONS: Describe the activity. If it is a new intervention, include references to any literature or research demonstrating its effectiveness. Include start and end dates for the activity, and the budget allocated to the activity, including—student equity and other funding**). If augmenting an existing program or activity, provide an overview of program history, date of implementation, relevant data on impact from research and evaluation, timeline and description of activity to be implemented with student equity funding, and budget including expenditures of student equity funding and other program funding**, including a description of how student equity funds will not be supplanting other district funds. Planned expenditures should be listed here as well as in the Student Equity Plan Summary Budget spreadsheet.
*Activity Type reflects state-provided categories and are coded as follows: (1) curriculum/course development or adaptation, (2) direct student support, (3) instructional support activities, (4) outreach, (5) professional development, (6) research and evaluation, (7) student equity coordination/planning, and (8) student services or other categorical program.
Note: Increasing ESL/Basic English & Math completion rates go hand-in-hand as many students take 1+ developmental courses; and therefore, the following activities are planned to simultaneously address the aforementioned goals.
ID | Activity Type* | Target Group | # Students Affected | Start | End | Responsible Person/Team Lead | SAMPLE (for internal discussion purposes only) | Equity Funds | Other Funds
C.1.1 C.2.1 C.3.1 | 6,8 | African American and Latino/a students | TBD | April 2016 | June 2016 | TBD | Activity Implementation Plan: Multiple Measures Assessment Project (Pilot) De Anza College is one of 27 pilot colleges participating in the Multiple Measures Assessment Project (MMAP) as part of the Common Assessment Initiative (CAI). The MMAP project asks pilot colleges to analyze a retrospective cohort of students using the multiple measures rule sets, which uses high school courses, grades and overall GPA to predict students’ placement in college-level math and English courses. The rule set, or model, places students in a math and English course where their predicted success rate will be at least a 2.2 GPA. As part of the pilot project, De Anza will use the multiple measures model to place a cohort of students in spring 2016, and to implement 1 of 6 recommended Non-Cognitive Variable (NCV) scales to a cohort of students and report the responses to Cal-PASS Plus at the end of spring 2016. The data will be used to determine the value added of incorporating the NCV to the multiple measures model. At the conclusion of the pilot project, Cal-Pass Plus will provide college-level analysis to the pilot colleges and report its findings to the state. How does the activity link to the indicator goal? The activity could effectively place students in a higher math and/or English level; and therefore, saving students time and increasing their likelihood of throughput. What are the activity's metric/goal/evaluation? There will be [X] faculty member who will participate in the Multiple Measures Pilot. The institutional research team will analyze and share results of the pilot outcomes with the college. Pending the pilot project’s final outcomes, De Anza will consider potential revisions to its assessment testing. | 0 | 0
C.1.2 C.2.2 C.3.2 | 1,2,8 | African American and Latino/a students | TBD | September 2015 | June 2016 | TBD | Activity Implementation Plan: Expanding Learning Communities/Curricular Pathways Learning communities will retain [X] of its students. The learning communities that generally have high participation from African American and Latino/a students include: Latino/a Empowerment at De Anza (LEAD), Learning in Community (LinC), Puente Project, and Umoja Program. A new curricular pathway will be implemented to serve Student Athletes of Color, combining developmental Reading, English, Academic Support, Counseling, and Humanities (REACH). Faculty and staff from each program will work with newly hired SSSP and Student Equity counselors dedicated to African American and Latino/a students (see Activity B.1.1 and SSSP 15-16 plan). How does the activity link to the indicator goal? Participation and retention in the aforementioned programs will assist African American and Latino/a students stay on track as each of the program have built-in support from peer students and a dedicated counselor. What are the activity's metric/goal/evaluation? Each student success and retention program will track the number of African American and Latino/a students it will serve 2015-16 and provide reporting in their annual program review. | 0 | 0
C.1.3 C.2.3 C.3.3 | 1, 2, 6, 8 | African American and Latino/a students | TBD | January 2016 | June 2016 | TBD | Activity Implementation Plan: Exit Survey (for dropped classes) About 75 percent of all De Anza students are placed into at least one developmental course. Since basic skills courses are precursors into degree/certificate-applicable courses, students’ success in basic skills could positively or negatively shape their educational outlook and progress. The Developmental and Readiness Education (DARE) Taskforce was formed to provide guidance and oversight on all basic skills initiatives on campus. De Anza students are able to drop a class via MyPortal, but their reason for dropping the class has not been tracked. For this reason, the DARE Taskforce requested for an exit survey to be developed. The purpose of the exit survey is to obtain and evaluate students’ reasons for dropping classes in basic skills English Writing, Reading, Language Arts, ESL, and Math. The planning and logistics for the exit survey is in progress and is scheduled to deploy by winter 2016 quarter. How does the activity link to the indicator goal? The data from the exit survey will be used to assess course scheduling and program reviews. What are the activity's metric/goal/evaluation? The student equity research analyst will provide data analysis to the DARE Taskforce equity and student success and support advisory committees at the end of each quarter. | 0 | 0
C.1.4 C.2.4 C.3.4 | 1, 3, 5, 8 | Faculty and Staff | TBD | January 2016 | June 2016 | TBD | Activity Implementation Plan: Faculty/Staff Inquiry Tool In winter 2016, De Anza will launch an internal web-based reporting tool where faculty, administrators, and staff can access data from completed (graded) terms up to the previous 3 years, on specific student outcome measures, such as enrollment, success, and retention. They will have the capability to (1) disaggregate the data by various student characteristics/groupings, (2) disaggregate the data by various course characteristics, (3) compare outcomes between select courses and student groups, and (4) compare their own section to all other sections aggregated. Faculty, administrators, and staff will need to sign-in via their MyPortal Employee tab in order to access the inquiry tool. Training will be conducted in phases, and the roll-out will include about 75-100 employees. How does the activity link to the indicator goal? The activity provides employees with convenient, end-of-term access to their student outcomes, disaggregated by course and student characteristics, to aid in the exploration of equitable outcomes for all students. What are the activity's metric/goal/evaluation? The student equity research analyst will track the number of employees who utilize the tool. Additionally, an annual survey will be sent to users to capture feedback on how they used the tool, if any curricular or programmatic changes were made based on information from the tool, and what type of reflection and dialogue stemmed from the information they gathered. | 0 | 0
C.1.5 C.2.5 C.3.5 | 1, 3, 5, 8 | Faculty and Staff | TBD | TBD | June 2016 | TBD | Activity Implementation Plan: English and Math Readiness Summer Jams For the 2015-16 academic year, the Developmental and Readiness Education Taskforce (DARE) will continue its basic skills initiative by partnering with English, ESL, Reading, Math, Counseling, and Outreach and Relations with Schools to research, develop, and implement two four-day boot camps/jams to incoming first-year students. These boot camps/jams will provide workshops on English and Math Readiness, placement and assessment, and introduce students to support services, learning communities with basic skills preparedness, and career programs. How does the activity link to the indicator goal? The DARE Taskforce provides oversight on campus-wide basic skills initiatives with student equity in mind. What are the activity's metric/goal/evaluation? The student equity research analyst will analyze and compare the basic skills course completion and persistence rates of English and Math Readiness Summer Jam participants to non-Summer Jam students. The goal is to have Summer Jam participants complete and persist at higher rates than non-Summer Jam participants. The results will serve as baseline and be used for future Summer Jam program evaluation. | 0 | 0
C.1.6 C.2.6 C.3.6 | 6 | TBD | TBD | September 2015 | June 2016 | L. Ly | Activity Implementation Plan: Student Equity Research Analyst The Office of Instruction has hired a research analyst to support state-mandated equity reporting. In addition, the research analyst is building rapport and working with various college areas and programs to communicate the equity analysis and help embed evaluation/metrics into program activities that support and enhances equity initiatives. How does the activity link to the indicator goal? The research analyst is communicating equity findings on the equity plan target groups: African Americans, Filipinos, Latino/a, disabled, foster youth, low income, and veterans. What are the activity's metric/goal/evaluation? The research analyst provides equity data analysis during spring and fall quarters when the Equity Plan is undergoing planning and reporting to the governance groups. In addition, the research analyst provides ad hoc equity analysis as needed. | 0 | 0
C.1.7 C.2.7 C.3.7 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Director of Student Success and Retention Services The Academic Services division will hire (1) Director of Student Success and Retention Services to coordinate and expand Summer Bridge, First Year Experience, Puente Project, and Umoja program within the context of SSSP and Student Equity initiatives. The Director will collaborate with SSRS counselors/coordinators, Learning in Communities, Student Success Center, and Instructional departments to track students' course and degree/certification completion. How does the activity link to the indicator goal? The Director of Student Success and Retention Services will be additional support team member to assist with student success and equity initiatives. What are the activity's metric/goal/evaluation? Each learning community program will track the number of African American, Filipino, and Latino/a students it will serve in 2015-16 and their associated course and degree/certification completion rates, and provide reporting in their annual program review. The student equity research analyst will analyze course and degree/certification completion for the state-mandated Equity Plan and Scorecard submissions. | 0 | 0
C.1.8 C.2.8 C.3.8 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Director of STEM Pathways The Physical Sciences, Mathematics, and Engineering Division will hire [1] Director of STEM Pathways to coordinate the Statway and Math Performance and Success programs to ensure access and quality instruction for African American, Filipino, and Latino/a students. The Director will develop campus partnerships with SSRS programs, Learning in Communities, Outreach and Relations with Schools, Business/Computer Science, and Biological and Health Sciences. How does the activity link to the indicator goal? The Director of STEM Pathways will be additional support team members to assist with student success and equity initiatives. What are the activity's metric/goal/evaluation? The Director of STEM Pathways will track the number of African American, Filipino, and Latino/a students it will serve in 2015-16 and their associated course and degree/certification completion rates, and provide reporting in their annual program review. The student equity research analyst will analyze course and degree/certification completion for the state-mandated Equity Plan and Scorecard submissions. | 0 | 0
C.1.9 C.2.9 C.3.9 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Student Equity Initiatives Program Coordinator II The Office of Equity, Social Justice, and Multicultural Education will hire a program coordinator II to support the college's student equity planning initiatives and activities. The equity program coordinator will assist with creating linkages among student success programs, professional development trainings, and overall strategic planning and implementation. How does the activity link to the indicator goal? The program coordinator II will work specifically with students, faculty, and classified professional on strategies for apply our conceptual framework, campus-wide collaborations, and high impact practices that could be utilized to support our identified target populations. What are the activity's metric/goal/evaluation? The program coordinator II will assist with the delivery of professional development trainings and programs as well as provide coaching as needed; and the student equity research analyst will analyze and compare the impact on the select indicators as they correspond with the identified trainings/programs/coaching per the rates of faculty participating in these trainings to those not able to participate. The goal is to have identified indicators impacted per the rates of faculty participating in equity and cultural responsiveness professional development trainings be higher than their counterpart. | 0 | 0
C.1.10 C.2.10 C.3.10 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Equity Office Administrative Assistant The Office of Equity, Social Justice, and Multicultural Education will hire a half-time administrative assistant to support the equity office and staff development office in meeting the college's equity planning goals and activities. The equity administrative assistant will specifically assist with budget tracking, record keeping, contracting, conference/training/workshop logistics, scheduling, and related office administration. The administrative assistant will also support linkages between the equity office and staff development, which includes assisting with Partners In Learning, Service Excellence, and related equity programs that emphasize supporting classified professionals in creating a welcoming environment for students and identifying linkages to the indicators. How does the activity link to the indicator goal? The program administrative assistant will work specifically with the equity office as well as those accessing services from these campus-wide offices. What are the activity's metric/goal/evaluation? The program assistant will assist with all related equity programming and services related to the state equity report initiatives; and the student equity research analyst will analyze and compare the impact on the select indicators as they correspond with the identified trainings/programs/coaching per the rates of faculty participating in these trainings to those not able to participate. The goal is to have identified indicators impacted per the rates of faculty participating in equity and cultural responsiveness professional development trainings be higher than their counterpart. | 0 | 0
DRAFT - WORK IN PROGRESS

## 5. Degree & Certificate
2015-16 Goals, Activities, Funding, and Evaluation
Indicator D.1 |  | Degree & Certificate Completion
Indicator Goal |  | To improve degree and certificate completion rates for African American, Filipino, and Latino/a students who experience disproportionate impact
Target Populations |  | African American |  |  | Filipino |  | Latino/a
Gap, Year |  | 80% index = 0.60, 2012-13 |  |  | 80% index = 0.67, 2012-13 |  | 80% index = 0.60, 2012-13
Target Population Goal |  | Degree/Certificate completion rates will increase by 1%, bringing the proportionality indexes for African American students to ≥ 1.00, for Filipino students to ≥ 0.95, and Latino/a students to ≥ 0.80
Target Goal Year |  | 2020
DIRECTIONS: Describe the activity. If it is a new intervention, include references to any literature or research demonstrating its effectiveness. Include start and end dates for the activity, and the budget allocated to the activity, including—student equity and other funding**). If augmenting an existing program or activity, provide an overview of program history, date of implementation, relevant data on impact from research and evaluation, timeline and description of activity to be implemented with student equity funding, and budget including expenditures of student equity funding and other program funding**, including a description of how student equity funds will not be supplanting other district funds. Planned expenditures should be listed here as well as in the Student Equity Plan Summary Budget spreadsheet.
*Activity Type reflects state-provided categories and are coded as follows: (1) curriculum/course development or adaptation, (2) direct student support, (3) instructional support activities, (4) outreach, (5) professional development, (6) research and evaluation, (7) student equity coordination/planning, and (8) student services or other categorical program.
ID | Activity Type* | Target Group | # Students Affected | Start | End | Responsible Person/Team Lead | SAMPLE (for internal discussion purposes only) | Equity Funds | Other Funds
D.1.1 | 2, 6, 8 | African American, Filipino, and Latino/a students | TBD | TBD | TBD | TBD | Activity Implementation Plan: DegreeWorks Audit by Admissions & Records The Admissions and Records (A&R) team will run a report [frequency TBD] of students with enough credits to receive a degree or certificate, and alert these students to file for a degree or certificate completion. How does the activity link to the indicator goal? The DegreeWorks audit by the Admissions and Records team will serve as another touch point to ensure students achieve their educational goal. The A&R team will be able to assist students to file for a degree or certificate, and refer students to see their academic counselors/advisors if they opt not to file due to changes in educational goals, majors, etc. What are the activity's metric/goal/evaluation? The A&R team will track the number of students who file for degree and certificate as part of their program review. The student equity research analyst will analyze degree and certificate completion rates for the state-mandated Equity Plan and Scorecard submissions. | 0 | 0
D.1.2 | 2, 6, 7, 8 | African American, Filipino, and Latino/a students | TBD | November 2015 | December 2016 | TBD | Activity Implementation Plan: Director of STEM Pathways The Physical Sciences, Mathematics, and Engineering Division will hire [1] Director of STEM Pathways to coordinate the Statway and Math Performance and Success programs to ensure access and quality instruction for African American, Filipino, and Latino/a students. The Director will develop campus partnerships with SSRS programs, Learning in Communities, Outreach and Relations with Schools, Business/Computer Science, and Biological and Health Sciences. How does the activity link to the indicator goal? The Director of STEM Pathways will be additional support team members to assist with student success and equity initiatives. What are the activity's metric/goal/evaluation? The Director of STEM Pathways will track the number of African American, Filipino, and Latino/a students it will serve in 2015-16 and their associated course and degree/certification completion rates, and provide reporting in their annual program review. The student equity research analyst will analyze course and degree/certification completion for the state-mandated Equity Plan and Scorecard submissions. | 0 | 0
D.1.3 | 2, 6, 7, 8 | African American, Filipino, and Latino/a students | TBD | November 2015 | December 2016 | TBD | Activity Implementation Plan: Director of Student Success and Retention Services The Academic Services division will hire (1) Director of Student Success and Retention Services to coordinate and expand Summer Bridge, First Year Experience, Puente Project, and Umoja program within the context of SSSP and Student Equity initiatives. The Director will collaborate with SSRS counselors/coordinators, Learning in Communities, Student Success Center, and Instructional departments to track students' course and degree/certification completion. How does the activity link to the indicator goal? The Director of Student Success and Retention Services will be additional support team member to assist with student success and equity initiatives. What are the activity's metric/goal/evaluation? Each learning community program will track the number of African American, Filipino, and Latino/a students it will serve in 2015-16 and their associated course and degree/certification completion rates, and provide reporting in their annual program review. The student equity research analyst will analyze course and degree/certification completion for the state-mandated Equity Plan and Scorecard submissions. | 0 | 0
D.1.4 | 6 | TBD | TBD | September 2015 | June 2016 | L. Ly | Activity Implementation Plan: Student Equity Research Analyst The Office of Instruction has hired a research analyst to support state-mandated equity reporting. In addition, the research analyst is building rapport and working with various college areas and programs to communicate the equity analysis and help embed evaluation/metrics into program activities that support and enhances equity initiatives. How does the activity link to the indicator goal? The research analyst is communicating equity findings on the equity plan target groups: African Americans, Filipinos, Latino/a, disabled, foster youth, low income, and veterans. What are the activity's metric/goal/evaluation? The research analyst provides equity data analysis during spring and fall quarters when the Equity Plan is undergoing planning and reporting to the governance groups. In addition, the research analyst provides ad hoc equity analysis as needed. | 0 | 0
D.1.5 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Student Equity Initiatives Program Coordinator II The Office of Equity, Social Justice, and Multicultural Education will hire a program coordinator II to support the college's student equity planning initiatives and activities. The equity program coordinator will assist with creating linkages among student success programs, professional development trainings, and overall strategic planning and implementation. How does the activity link to the indicator goal? The program coordinator II will work specifically with students, faculty, and classified professional on strategies for apply our conceptual framework, campus-wide collaborations, and high impact practices that could be utilized to support our identified target populations. What are the activity's metric/goal/evaluation? The program coordinator II will assist with the delivery of professional development trainings and programs as well as provide coaching as needed; and the student equity research analyst will analyze and compare the impact on the select indicators as they correspond with the identified trainings/programs/coaching per the rates of faculty participating in these trainings to those not able to participate. The goal is to have identified indicators impacted per the rates of faculty participating in equity and cultural responsiveness professional development trainings be higher than their counterpart. | 0 | 0
D.1.6 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Equity Office Administrative Assistant The Office of Equity, Social Justice, and Multicultural Education will hire a half-time administrative assistant to support the equity office and staff development office in meeting the college's equity planning goals and activities. The equity administrative assistant will specifically assist with budget tracking, record keeping, contracting, conference/training/workshop logistics, scheduling, and related office administration. The administrative assistant will also support linkages between the equity office and staff development, which includes assisting with Partners In Learning, Service Excellence, and related equity programs that emphasize supporting classified professionals in creating a welcoming environment for students and identifying linkages to the indicators. How does the activity link to the indicator goal? The program administrative assistant will work specifically with the equity office as well as those accessing services from these campus-wide offices. What are the activity's metric/goal/evaluation? The program assistant will assist with all related equity programming and services related to the state equity report initiatives; and the student equity research analyst will analyze and compare the impact on the select indicators as they correspond with the identified trainings/programs/coaching per the rates of faculty participating in these trainings to those not able to participate. The goal is to have identified indicators impacted per the rates of faculty participating in equity and cultural responsiveness professional development trainings be higher than their counterpart. | 0 | 0
D.1.7 | TBD | TBD | TBD | TBD | TBD | TBD |  | 0 | 0
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS

## 6. Transfer
2015-16 Goals, Activities, Funding, and Evaluation
Indicator E.1 |  | Transfer
Indicator Goal |  | To improve transfer rates for African American, Filipino, and Latino/a students who experience disproportionate impact
Target Populations |  | African American |  |  | Filipino |  | Latino/a
Gap, Year |  | 80% index = 0.61, 2012-13 |  |  | 80% index = 0.60, 2012-13 |  | 80% index = 0.63, 2012-13
Target Population Goal |  | Transfer rates will increase by 1%, bringing the proportionality indexes for African American students to ≥ 1.00, for Filipino students to ≥ 0.90, and Latino/a students to ≥ 0.85
Target Goal Year |  | 2020
DIRECTIONS: Describe the activity. If it is a new intervention, include references to any literature or research demonstrating its effectiveness. Include start and end dates for the activity, and the budget allocated to the activity, including—student equity and other funding**). If augmenting an existing program or activity, provide an overview of program history, date of implementation, relevant data on impact from research and evaluation, timeline and description of activity to be implemented with student equity funding, and budget including expenditures of student equity funding and other program funding**, including a description of how student equity funds will not be supplanting other district funds. Planned expenditures should be listed here as well as in the Student Equity Plan Summary Budget spreadsheet.
*Activity Type reflects state-provided categories and are coded as follows: (1) curriculum/course development or adaptation, (2) direct student support, (3) instructional support activities, (4) outreach, (5) professional development, (6) research and evaluation, (7) student equity coordination/planning, and (8) student services or other categorical program.
ID | Activity Type* | Target Group | # Students Affected | Start | End | Responsible Person/Team Lead | SAMPLE (for internal discussion purposes only) | Equity Funds | Other Funds
E.1.1 | 2, 6, 7, 8 | African American, Filipino, and Latino/a students | TBD | TBD | TBD | TBD | Activity Implementation Plan: Transfer Center The transfer center will designate a counselor(s) to collaborate with Admissions and Records to increase the number of transferred students, and to plan and coordinate outreach opportunities for students to visit four-year institutions. How does the activity link to the indicator goal? The transfer center counselor will be another support team member to assist with student success and equity initiatives. What are the activity's metric/goal/evaluation? The transfer center will track the number of African American, Filipino, and Latino/a students it serves and their associated transfer rates, and provide reporting in their annual program review. The student equity research analyst will analyze transfer rates for the state-mandated Equity Plan and Scorecard submissions. | 0 | 0
E.1.2 | 2, 3 | Faculty | TBD | TBD | TBD | TBD | Activity Implementation Plan: Faculty & Staff Advisor Panel for Career Exploration [X] faculty and staff from various disciplinary backgrounds will serve as guest lecturers and/or sit on panels and provide [X] hours per week to discuss career aspirations and questions with students. How does the activity link to the indicator goal? The advisor panel enables faculty another touch point to build rapport with students, share their professional track, and inform students what career options are available to them if they were to pursue a degree/certificate in a particular discipline. What are the activity's metric/goal/evaluation? [X] will track the number of African American, Filipino, and Latino/a students it will serve 2015-16 and provide reporting in their annual program review. | 0 | 0
E.1.3 | 6 | TBD | TBD | TBD | TBD | L. Ly | Activity Implementation Plan: Disaggregate Asian Transfer Rate (International vs. Domestic Students and by Asian Ethnic Subgroups) The student equity research analyst will disaggregate the Asian transfer data to determine whether international students and a particular Asian subgroup are skewing the results. How does the activity link to the indicator goal? The analysis will identify any equity gaps in transfer rates among the Asian student population. What are the activity's metric/goal/evaluation? Pending results, findings will inform discussion and areas for improvements. | 0 | 0
E.1.4 | 6 | TBD | TBD | September 2015 | June 2016 | L. Ly | Activity Implementation Plan: Student Equity Research Analyst The Office of Instruction has hired a research analyst to support state-mandated equity reporting. In addition, the research analyst is building rapport and working with various college areas and programs to communicate the equity analysis and help embed evaluation/metrics into program activities that support and enhances equity initiatives. How does the activity link to the indicator goal? The research analyst is communicating equity findings on the equity plan target groups: African Americans, Filipinos, Latino/a, disabled, foster youth, low income, and veterans. What are the activity's metric/goal/evaluation? The research analyst provides equity data analysis during spring and fall quarters when the Equity Plan is undergoing planning and reporting to the governance groups. In addition, the research analyst provides ad hoc equity analysis as needed. | 0 | 0
E.1.5 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Director of Student Success and Retention Services The Academic Services division will hire (1) Director of Student Success and Retention Services to coordinate and expand Summer Bridge, First Year Experience, Puente Project, and Umoja program within the context of SSSP and Student Equity initiatives. The Director will collaborate with SSRS counselors/coordinators, Learning in Communities, Student Success Center, and Instructional departments to track students' course and degree/certification completion. How does the activity link to the indicator goal? The Director of Student Success and Retention Services will be additional support team member to assist with student success and equity initiatives. What are the activity's metric/goal/evaluation? Each learning community program will track the number of African American, Filipino, and Latino/a students it will serve in 2015-16 and their associated course and degree/certification completion rates, and provide reporting in their annual program review. The student equity research analyst will analyze course and degree/certification completion for the state-mandated Equity Plan and Scorecard submissions. | 0 | 0
E.1.6 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Director of STEM Pathways The Physical Sciences, Mathematics, and Engineering Division will hire [1] Director of STEM Pathways to coordinate the Statway and Math Performance and Success programs to ensure access and quality instruction for African American, Filipino, and Latino/a students. The Director will develop campus partnerships with SSRS programs, Learning in Communities, Outreach and Relations with Schools, Business/Computer Science, and Biological and Health Sciences. How does the activity link to the indicator goal? The Director of STEM Pathways will be additional support team members to assist with student success and equity initiatives. What are the activity's metric/goal/evaluation? The Director of STEM Pathways will track the number of African American, Filipino, and Latino/a students it will serve in 2015-16 and their associated course and degree/certification completion rates, and provide reporting in their annual program review. The student equity research analyst will analyze course and degree/certification completion for the state-mandated Equity Plan and Scorecard submissions. | 0 | 0
E.1.7 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Student Equity Initiatives Program Coordinator II The Office of Equity, Social Justice, and Multicultural Education will hire a program coordinator II to support the college's student equity planning initiatives and activities. The equity program coordinator will assist with creating linkages among student success programs, professional development trainings, and overall strategic planning and implementation. How does the activity link to the indicator goal? The program coordinator II will work specifically with students, faculty, and classified professional on strategies for apply our conceptual framework, campus-wide collaborations, and high impact practices that could be utilized to support our identified target populations. What are the activity's metric/goal/evaluation? The program coordinator II will assist with the delivery of professional development trainings and programs as well as provide coaching as needed; and the student equity research analyst will analyze and compare the impact on the select indicators as they correspond with the identified trainings/programs/coaching per the rates of faculty participating in these trainings to those not able to participate. The goal is to have identified indicators impacted per the rates of faculty participating in equity and cultural responsiveness professional development trainings be higher than their counterpart. | 0 | 0
E.1.8 | TBD | TBD | TBD | TBD | TBD | TBD | Activity Implementation Plan: Equity Office Administrative Assistant The Office of Equity, Social Justice, and Multicultural Education will hire a half-time administrative assistant to support the equity office and staff development office in meeting the college's equity planning goals and activities. The equity administrative assistant will specifically assist with budget tracking, record keeping, contracting, conference/training/workshop logistics, scheduling, and related office administration. The administrative assistant will also support linkages between the equity office and staff development, which includes assisting with Partners In Learning, Service Excellence, and related equity programs that emphasize supporting classified professionals in creating a welcoming environment for students and identifying linkages to the indicators. How does the activity link to the indicator goal? The program administrative assistant will work specifically with the equity office as well as those accessing services from these campus-wide offices. What are the activity's metric/goal/evaluation? The program assistant will assist with all related equity programming and services related to the state equity report initiatives; and the student equity research analyst will analyze and compare the impact on the select indicators as they correspond with the identified trainings/programs/coaching per the rates of faculty participating in these trainings to those not able to participate. The goal is to have identified indicators impacted per the rates of faculty participating in equity and cultural responsiveness professional development trainings be higher than their counterpart. | 0 | 0
E.1.9 | TBD | TBD | TBD | TBD | TBD | TBD |  | 0 | 0
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS
DRAFT - WORK IN PROGRESS