## Multimedia
Target date | Project Details | Division | Room | New or Refresh | Funding Source | Notes
In Progress
| Swing Space Room request Fall Quarter |  |  |  |  | Necessary for M-Th installs
Fall Quarter 2011
Fall Term 2011* | Full multimedia system with Spectrum cart | Creative Arts | ATC307 | New | Measure C | PO issued, waiting for scheduling 9-19-11
Fall Term 2011* | Full multimedia system refresh | PSME | E36 | Refresh | Measure C | PO issued, waiting for scheduling 9-19-11
Fall Term 2011* | Full multimedia projection w\special audio | Creative Arts | A31 | New | Measure C | PO issued, waiting for scheduling 9-19-11
Fall Term 2011* | Extron Digital Switcher with 70" LCD | Creative Arts | A93 | Refresh | Measure C | PO issued, waiting for scheduling 9-19-11
Fall Term 2011* | Full multimedia system with Spectrum cart |  | G8 | New | Measure C | PO issued, waiting for scheduling 9-19-11
Fall Term 2011* | Full multimedia system refresh |  | G10 | Refresh | Measure C | PO issued, waiting for scheduling 9-19-11
Fall Term 2011* | Full multimedia system with Spectrum cart | Swing Space | MQ2A | New | Measure C | PO issued, waiting for scheduling 9-19-11
Fall Term 2011* | Large LCD Display with mobile cart | Auto-Tech | E12F | New | Measure C | PO issued, waiting for scheduling 9-19-11
*Moved from Summer Break 2011
Winter Break 2011
Winter Break 2011 | Digital HD projection, Crestron Controller with touch panel | Creative Arts | ATC 107 | Refresh | Measure C | In progress, pending approval 10-7-11
Winter Break 2011 | Digital HD projection, Crestron Controller with touch panel | Creative Arts | ATC115 | Refresh | Measure C | In progress, pending approval 10-7-11
Winter Break 2011 | Multimedia system |  | CHC | New | Measure C | Site walk pending 10-11-11
Winter Break 2011 | Two projector system with smartboard and audio conference capability | DASB | DASB Chambers | New | ? | Design completed, waiting for quote 10-11-11
Winter Break 2011 | Multimedia system | Bio\Health | ESA | Refresh | Measure C | Site walk pending 10-11-11
Winter Break 2011 | A side projector refresh, wireless mics upgrade, screen control, block off plates for tamper control |  | CONF AB | Refresh | Measure C | Waiting for revised quote 10-11-11
Winter Quarter 2012
Winter Term 2012** | Full multimedia system |  | L43 | New | Measure C | Site walk completed 7-21-11
Winter Term 2012** | Full multimedia system |  | L82 | New | Measure C | Site walk completed 7-21-11
Winter Term 2012** | Full multimedia system |  | L83 | New | Measure C | Site walk completed 7-21-11
Winter Term 2012** | Full multimedia refresh (ETS request) | SSH | S56 | Refresh | Measure C | Site walk completed 7-21-11
Winter Term 2012** | Full multimedia refresh (ETS request) | PSME | E31 | Refresh | Measure C | Site walk completed 7-21-11
**Moved from Fall Quarter 2011
Spring Break 2012
Summer Break 2011 | Sim Man\Sim Baby - simulation of man and baby with multiple camera, microphones and flat screen displays. | Nursing | S82 (double/triple effort) | New | Measure C | Pending Bid 10-11-11, need update | Janet will speak w// dept since Bill M. is on vacatoin; 42" Flat Screen Display (Mult diplays); Old PR # R124578; Flat Screen and Cameras.; Sl 042310 Ed working on the design - location of he flat screen - Bill will follow up w/ Ed.; SL 081710 Formal Bid sent to Purchasing
Spring Quarter 2012
Summer Quarter 2012
Summer Break 2012
New Requests
| Outdoor projection system | Bio\Health | Kirsch Portable | New | Measure C | Portable system, equipment for outdoor use
| Multimedia system with mobile lectern | Bio\Health | Kirsch Open Staff Area | New | Measure C | Recommend large LCD with Spectrum Lectern
| Flat panel displays (7) for fitness center | PE | Fitness Center | Refesh | Measure C | waiting to be prioritized at Dean's meeting.
| Flat panel displays (9) for locker rooms | PE | locker rooms | Refesh | Measure C | waiting to be prioritized at Dean's meeting.

## completed
Target date | Project Details | Division | Room | New or Refresh | Funding Source | Notes
Spring Term
Spring Term 2011 | Full multimedia system | Baldwin Winery | Conference room | New | MC | completed
Spring Break
Spring Break 2011 | Dual projection system with Spectrum cart | General | L47 | New | MC | Spectrum Cart with full MM system - dual projection system; PO issued; computer rec'd; probably will get done in Winter Term
Spring Break 2011 | Full multimedia refresh | Lang Art | L49 | Refresh | MC | Full system refresh; PR done waiting on PO; computer rec'd
Spring Break 2011 | Full multimedia refresh | Lang Art | L81 | Refresh | MC | Full system refresh; PR done
Spring Break 2011 | Full multimedia refresh | PSME | S16 | Refresh | MC | Full system refresh; PR done
Spring Break 2011 | AV Rover cart w\iMac and doc cam | Swing | MQ2A | New | NA | moved from L47
| laptop input image poor,service call | Gilbane | ADM 106 | service | NA | Swap cable with doc camera since projector showing blue image. Used by Gilbane and not using doc camera. Final fix after Gilbane vacates the room a few years from now.
Spring Break 2011 | Projector, speakers, input plate | Palo Alto Univ | LC 138 | New | PA Univ | completed
Spring Quarter 2011
Spring Term 2011 | Full multimedia system with Spectrum cart | swing space | MQ2 | New | Measure C | completed
Spring Term 2011 | Full multimedia system with Spectrum cart | swing space | MQ3 | New | Measure C | completed
| AV Rover and projector for loaner inventory | NA | Floating Cart | New | Measure C | AV Rover is located at DA Audio Visual
Spring Term 2011 | Full multimedia system | CHC | East Cottage Classroom | New | Measure C | completed 9-19-11
Spring Term 2011 | Full multimedia system | CHC | East Cottage Resouce Room | New | Measure C | completed 9-19-11
Summer Quarter 2011
Summer Term 2011 | Full multimedia system | Language Arts | L31 | New | Measure C | Completed 9-26-11
Summer Term 2011 | Full multimedia system | Language Arts | L32 | New | Measure C | Completed 9-26-11
Summer Term 2011 | Full multimedia system | Language Arts | L34 | New | Measure C | Completed 9-26-11
Summer Term 2011 | Full multimedia system | Language Arts | L35 | New | Measure C | Completed 9-26-11
Summer Term 2011 | Full multimedia system | Language Arts | L36 | New | Measure C | Completed 9-26-11
Summer Break 2011
Summer Break 2011 | Remove\Protect MM to allow for painting and carpet and tile replacement starting Summer Break De-Install/Reinstall | Language Arts | L Quad |  | Measure C | Completed 9-26-11
Summer Break 2011 | Remove\Protect MM for sound attenuation project starting Summer Break. De-Install/Reinstall | PSME\Bio Health | S Quad |  | Measure C | Completed 9-26-11
Spring Term 2011 | Projector and document camera upgrade | Bio\Health | SC1102 | Refresh | Measure C | Completed 9-26-11 | moved from Spring quarter due to scheduling
Summer Break 2011 | Digital HD projection, 7.1 Surround Sound System, Crestron Controller with touch panel | Create Arts | ATC 120 | Refresh | Measure C | Completed 9-26-11
Summer Break 2011 | Full multimedia system | Language Arts | L62 | New | Measure C | Completed 9-26-11
Summer Break 2011 | Full multimedia system | Language Arts | L63 | New | Measure C | Completed 9-26-11
Summer Break 2011 | Full multimedia system | Language Arts | L64 | New | Measure C | Completed 9-26-11
Summer Break 2011 | Full multimedia system | Language Arts | L65 | New | Measure C | Completed 9-26-11
Summer Term 2011 | Full multimedia system | Language Arts | L75 | New | Measure C | Completed 9-26-11 | moved from Summer quarter due to scheduling
Summer Break 2011 | Full multimedia system refresh |  | ADM 103 | Refresh | Measure C | Completed 9-26-11
Summer Break 2011 | Full multimedia system with Spectrum cart | Child Dev | CDC 110 | Refresh | Measure C | Completed 9-26-11
Summer Break 2011 | Full multimedia system refresh | PSME | E32 | Refresh | Measure C | Completed 9-26-11
Summer Break 2011 | Dual projection system with Spectrum cart | PSME | E35 | Refresh | Measure C | Completed 9-26-11
Summer Break 2011* | Full multimedia system refresh added because S-Quad project required equipment removal | PSME | S72 | Refresh | Measure C | Completed 9-26-11
Summer Break 2011* | Full multimedia system refresh added because S-Quad project required equipment removal | PSME | S75 | Refresh | Measure C | Completed 9-26-11
Summer Break 2011* | Re-install multimedia equipment | PSME | S54 | Refresh | Measure C | Completed 9-26-11
Summer Break 2011* | Window replacement project, remove and reinstall LCD displays |  | L&S quad |  | Measure C | Completed 9-26-11
Summer Break 2011* | Remove and re-install cameras for L-quad |  | L-Quad |  | Measure C | Completed 9-26-11
*added due to L-Quad and S-Quad projects
Cancelled
Summer Term 2011 | Small LCD display (need location of computer) | CHC | East Cottage Hallway | New | Measure C | added 6-2-11, site walk scheduled for 6-3-11, cancelled due to lack of funds 6-2-11

## Completed old
Scheduled | Priority | Division | Location | New or Replace | Date requested and requestor | Funding Source | Open for work | Comment
Fall Term 08 | 2 | PSME | Planetarium | R |  |  | Completed | Replacement Planetarium Upgrade Projector (per Bill 1/2 day); SL 101608Waiting on a Plasma to arrive Jeanine held up Req. That included projector -Then will schedule the Projector and plasma install Fall Term 08; SL 102908 should complete by 103108;
Fall Term 08 | 3 | C Arts | VPAC | N | Fall 08 | Measure C | Fall term/ Winter Break Complete | SL 102908 2 rooms - nonstandard; + dance cart during Winter Break; SL 012809 Euphrat needs to be tested; Dance cart - speakers needs to mounted; SL 021709 DSA rejected plan - need to regroup for a new plan
Winter Break 08 | 5 | BUS/CIS | AT 312 | R and N |  | Non-Measure C | Completed | Bill Matsumoto said needs projector replace $3852; SL 101608 Acutally need to replace the full system after assesment - not a full smart classroom and recommend to bring up to a full smart classroom capability; College needs to look at the funding and if want to increase the scope; Need about $15,000; non Measure C funded; Christina okayed to go ahead with change in scope; SL 101908 still needs to order console -so still in design phase 102908 - plan to do during Winter Break; if miss move to Winter Term; Available on Friday's after 10:30am - work w/ department to clear room for a day; SL 012809 On scheduel for 103009.
Winter Break 08 | 6 | PE | PE-12U | N |  | Measure C | Completed | On Bridge Allocation list but not current working list. see Jeff Forman per Rich Massage Therapy No Infrasture to support; SL 101608 No infrastructure Bill M. has an infrastructure assessment on 101708 - Want to find out how difficult it will be to install the infrastructure to support the projector - false ceiling with only 6" to a hard ceiling. Cabinets exist and could be used to store the MM equipment or will suggest a cart. Could move to Winter Term due to infrastructure challenge. SL 102908 SPL can do all the facilities work required. PR will go to Purchasing on Monday - Plan to install fall term/ winter break; but VPAC has a priority over this install; Available after 10:30am- work w/ department to clear room for a day; SL 012809 - DONE - key for the cabinet is missing - was locked and no one has key to unlock. Lydia will work it out to get it unlocked.
Winter Term 09 | 12 | BH | KC 112 | R |  | Non Measure C | Complete | Refresh Projector; SL 010509 needs to be invoicec by 5/15; Sl 021709 waiting to be scheduled.
Winter Term 09 | 13 | BH | KC120 | R |  | Non Measure C | Complete | Refresh Projector; SL 010509 needs to be invoicec by 5/15; Sl 021709 waiting to be scheduled.
Winter Term 09 | 14 | BH | KC239 | R |  | Non Measure C | Complete | Refresh Projector; SL 010509 needs to be invoicec by 5/15; Sl 021709 waiting to be scheduled. | PROJECTS FROM THIS LINE ABOVE WILL BLEED INTO SPRING TERM
|  | PSME | S41 |  |  | Measure C | Complete
|  | BH | S74 | N/R |  |  | Complete | 1/2 New & 1/2 Refresh
Winter Term 09 | 8 | CA | A92 | N |  | Measure C? | During Winter Term w/lab | Wired has screen needs equipment; SL 101608Prioritize for Winter Term 08 to align w/ Lab set up? Discuss in Dean's meeting; SL 012809 - PR in process; SL 021709 - PR into purchasing Nicole will check to see if PO was cut. Needed by Spring Term classes. SL 031809 plan to install next week
Spring Break 09 | 4 | Library | LC237 | R | Fall 08 | ? |  | SL 101608 Old projector - if replace console computer at same time as lab, the new computer and old projector are not compatible. No control system - just a projector; Late Fall Quarter the lab will be upgraded. Switching from PCs to Apples ; Discuss at Dean's meeting for Fall/Winter break 08; SL 012809 Upgrade projector - PR Is in process - Dead PRoejctor; Sl 021709 - portabel in use, PO has been cut.
Fall Term 08/ Complete except for training | Done | EOC | ADMIN 106&109 | N | Complete | ? | Fall/Winter Break | Emergency Operation Center 2LCDS RF cabling for ham radio; SL 101608 moved to Fall term 08; SL 102908 should be complete 110308; SL 012809 In Process - expect completion by Spring Break; SL 010709 looking at First week of March. SL 031809 DONE MM wise but Stan Judins will test the ham radio sytem; Need a training session with College; Need to rescan in June when analog goes to Digital; Sl 052009 Completed. There is an antenna for a ham radio but not ham radio. Need to follow up w/ Stan to see if he did test hte antenna w/ his ham radio; Stan Confirmed the antenna works.
Winter Break 08 | 7 | C Arts | A-11 | R | Complete | Non Measure C | Winter Break changed to Spring Break 09 | ETS will no longer support; SL 101608 - Very OLD system - if breaks will not be fixed. Need a complete refresh - have a prelim quote - need okay from Ed and Nancy C.; SL 102908 break/fix the projector on 10//28/08 so need to have it replaced during the Winter break and takes priority ver PE -12U.; SL 012809 Was completed but have change order from Dan Mitchell - how will it be funded - Dr. Canter will provide the information - Bill M. getting the quote.; SL 021709 PO out for Upgrade - install needs to be scheduled - waiting on equipment to be ordered and delivered for the Dan Mitchell modifications; otherwise was completed as originally planned; Sl 031809 - PO was created recently; SL 040809 waiting on a part
Spring Break 09 | 9 | BH | SC 1102 | N | Complete | Prop 55 | Early Spring Term to meet 5/15 deadline | SL 112008 Low Cost Web Archive Project; not started added to list on 112008; SL 010509 Bill M. will get a quote asap; SL 012809 Have final quote and need to submit PR.; Mac Mini - needed for this project. ; SL 021709 PR is with Purchasing - waiting for PO - Nicole will follow up. Bill gave Mac Mini PR to Nicole- this is in addtion to the DELL that's in the room. If the DELL needs to be upgraded, the College needs to determine this w/ Ed. The Mac Mini will capture the video and audio, the DELL will remain the computer connected to the projector; SL 031809 moved to early Spring Term - PRs are in to Purchasing
|  | Auto Tech | E1/Piercy Toyota | Move then Surplus |  | Measure C? | Spring / When they move out | Remove existing for renovation and put out at Piercy on table top - no install
Winter Term 09 | 10 | BH | KIRSCH 4 Lobby viewing spaces | N |  | Prop 55 | Early Spring Term to meet 5/15 deadline | Part of Original Building Plans Kirsch Video System on demand - Counts as 4 - Can be done Mid Quarter, Hallway mini viewing stations for faculty and students; SL 112008 not started added to list on 112008 adding new; 012809 Have final quote need to complete PR and confirm account code for funding.; SL 021709 PRs have been submitted last week.; SL 031809 plan for early Spring term; SL 052009 Waiting for a network connection - need to move a port.SL Still waiting for network port; SL 081109 complete
|  | Summer Term 09 | 16 | SS | G-4 | N |  | Measure C | Busy fridays until 2 | SL 112008 Moved up in list per Dean's meeting; STILL ON TRACK FOR SPRING TERM; SL 031609 Planning to do during Summer Term; SL 05209 Meeting w/ the Deans on Friday - 3 Deans share the space- Carolyn and Rowina (Nancy C. said will give input to Carolyn) - Will use it simliarly to Music room in VPAC; may move this project to summer break mainly due to the planning just happening now and the conversion of financials to Banner and the slow down in purchasing - lead times may be 16 weeks up from the 12 weeks. SL 060209 Waiting for a quote from the vendor. SL 081109 added new computer to lab/staff list. Still on track. SL 100109 Complete
|  | Summer Term 09 | 15 | SS | G-1 | N |  | Measure C | Open Fridays | SL 112008 Moved up in list per Dean's meeting; Needs a full day to install a full system; BASED ON WORK SHOULD PUSH TO A BREAK TIME - CAN'T BE DONE IN ONE DAY; BILL M. NEEDS TO MAKE ANOTHER ASSESSMENT ON CORRECT SOLUTION OF EQUIPMENT; SL 031609 Double wide classroom - need a full day - if can do during summer term - otherwise plan for summer break. Equal to 2 MM rooms of effort; sl 052009 Bill meeting w/ Deans on Friday 05/22/09; SL 060209 Waiting for a quote from the vendor. Maybe mid to late summer quarter.; SL still on track for summer 09 break; SL 100209 Complete
|  | Summer Break 09 | 17 | IIS | L-61 | N |  | Measure C | Busy fridays until 2 | MM playback in classrooms;SL 112008 Moved up in list per Dean's meeting; SL 060209 Bill will get quotes right after the G rooms. SL still on track for summer 09 break; ; SL 100209 Complete
|  | Summer Break 09 | 18 | IIS | L-66 | N |  | Measure C | Busy fridays until 1 | MM playback in classrooms; SL 112008 Moved up in list per Dean's meeting; SL 060209 Bill will get quotes right after the G rooms. ; SL 100209 Complete
|  | Summer Break 09 | 19 | SS | L-73 | N |  | Measure C | Busy fridays until 3 | SL 112008 Moved up in list per Dean's meeting; SL 060209 Bill will get quotes right after the G rooms. SL still on track for summer 09 break; SL 100209 Complete
| 11/5/2009-11/10/09 | SummerTerm 09/ Summer Break |  | LArts | ATC 102, 103 | N |  | Measure C |  | Adjoining Rooms (need at same time); Lab is being updated during Spring Break? If so then needs to be prioritized to line up w/ the Lab computers being updated - SL 012809; Need to verify the refresh needs - Bill M. work on this. Lydia will bring to Deans to see if want to line up w/ the computers being refreshed around Spring Break time 09; SL 021709 - Missed the lead time for Spring Break. There are no pathways so facilities issue - significant work required. Using a portable. Will decide when this will happen at a later date; SL 031809 Want to sync w/ the refresh of the lab computers; Buy projectors now to be compatible w/ computers, mount in Ceiling in Summer; SL 040809 - Quotes to Janet and Nicole - Janet follow up with Nicole on status of PRs - want to order asap then schedule - Order put at 4/13 FFE meeting; SL 05209 bought the projectors - have a temp set up plan to moutn new projectors over summer; Waiting for projectors to arrive; then will get a quote and account code to mount the projectors. SL 081109 Have projectors - labor needs to be resubmitted inBanner. SL 100209 Labor PRs and POs complete. Deploy in about 4 weeks. Sl 102909 PO issued wiating for SPL to provide an install date. SL 110909 Equipment in and working w/ George Hein to get time in the rooms.
| 11/18/09-12/20/09 | Fall Term 09/Winter Break 09 |  | Auto Tech | E1 Rm 7 / Machine shop/open area | N |  |  | Fall/December 09/ Need for Winter Term 10 | SL 100209 This is the new additional classroom that did not exist before the renovation - its in the new bldg; SL 100209 College will speak to Donna to discuss funding source; SL 102909 PO's have been placed waiting for install date from SPL; SL 111009 equipment has been ordered; final walk through this afternoon.
| Mid Nov. 2009 | Spring / Summer Term 09 |  | Jack Lynch - replaced Letha | ATC 202 | Replace | 2009-04-08 | PO# AA100415 |  | SL 040809 Jim H. reported projector will die anytime - want a new control system to support laptop - Bill will do an assessment then report back to Lydia for assement of funding. Min needs projector replaced.; SL 052009 Have PR for projector replacement. SL 060209 - at Purchasing waiting for PO. PR 128138 submitted on 061509; SL 081109 Needs to be resubmitted in Banner. SL 100209 Move projector back in the room to avoid purchasing a special lens - projector is dying/needs replacing. The wrong quote got attached to the PO. Need to do a change order to associate the correct quote for the PO - Purchasing creates the change order - Bill M. is authorized by the College to direct Purchsing to replace the quote with the correct quote. There is no change in cost. College needs to determine the correct funding source since the PO indicates it is non-measure C. SPL was told to place it on hold. Since the College wants to use Measure C Funds, this AA PO will be cancelled and a new Req. will be created with correct quote and Measure C funds. SL 102909 waiting for scheduling w SPL; SL 111009 waiting for SPL to receive equip.
| Fall Term 2009 | Emegency Repair |  |  | S34/S35 | Replace | ASAP - Emergency Repair | 766713/Measure C |  | SL 081109 These are the projectors in the cabinets that were designed wrong. The cabinets will be modified - need an account code to modify the cabinets; Bill send quote for projectors to Lydia; Bill M. put in request to Plant for estimate to modify the cabinets and will forward to Lydia, Letha, and Janet; Sl 102909 Work order in to modify the cabinets; replacement projectors on order; SL 110909 Cabinets are being modified. Equipment has arrived. SL 111009 first cabinet was modified yesterday; 2nd cabinet will be modified today. Looking for a opening to install the equipment - need both rooms for the entire day. Lydia will get back to us today about Jim and Bill working overtime this Friday - holiday to have these rooms completed.
| 11/18/09-12/20/09 | Fall Term 09/Winter Break 09 |  | Auto Tech | E1 Rm 12a | R |  | Measure C 766713; | Fall/December 09/ Need for Winter Term 10 | Replace/Refresh 5 Existing Projectors; SL 021809 1 of six rooms; SL 040809 Need a meeting w/ Users to discuss plan for renovated rooms; SL 100209 Bill and Jose did a site walk with usersto confirm needs. Bill getting quote from SPL. This is a refresh of equipment. SL 102909 PO's have been placed waiting for install date from SPL; SL 111009 equipment has been ordered; final walk through this afternoon. SL012210 waiting on doc cameras sched. for next Tues.
| 11/18/09-12/20/09 | Fall Term 09/Winter Break 09 |  | Auto Tech | E1 Rm 12b | R |  |  | Fall/December 09/ Need for Winter Term 10 | Replace/Refresh 5 Existing Projectors; SL 021809 2 of six rooms; SL 100209 College will speak to Donna to discuss funding source; SL 102909 PO's have been placed waiting for install date from SPL; SL 111009 equipment has been ordered; final walk through this afternoon. SL012210 waiting on doc cameras sched. for next Tues.
| 11/18/09-12/20/09 | Fall Term 09/Winter Break 09 |  | Auto Tech | E1 Rm 12c | R |  |  | Fall/December 09/ Need for Winter Term 10 | Replace/Refresh 5 Existing Projectors; SL 021809 3 of six rooms;SL 100209 College will speak to Donna to discuss funding source; SL 102909 PO's have been placed waiting for install date from SPL; SL 111009 equipment has been ordered; final walk through this afternoon.SL012210 waiting on doc cameras sched. for next Tues.
| 11/18/09-12/20/09 | Fall Term 09/Winter Break 09 |  | Auto Tech | E1 Rm 12d | R |  |  | Fall/December 09/ Need for Winter Term 10 | Replace/Refresh 5 Existing Projectors; SL 021809 4 of six rooms; SL 100209 College will speak to Donna to discuss funding source; SL 102909 PO's have been placed waiting for install date from SPL; SL 111009 equipment has been ordered; final walk through this afternoon.SL012210 waiting on doc cameras sched. for next Tues.
| 11/18/09-12/20/09 | Fall Term 09/Winter Break 09 |  | Auto Tech | E1 Rm 12e | R |  |  | Fall/December 09/ Need for Winter Term 10 | Replace/Refresh 5 Existing Projectors; SL 021809 5 of six rooms; SL 100209 College will speak to Donna to discuss funding source; SL 102909 PO's have been placed waiting for install date from SPL;SL 111009 equipment has been ordered; final walk through this afternoon.
| 11/18/09-12/20/09 | Fall Term 09/Winter Break 09 |  | Auto Tech | E1 Rm 16 (addition) | N |  |  | Fall/December 09/ Need for Winter Term 10 | SL 100209 This is the new additional classroom that did not exist before the renovation - its in the new bldg; SL 100209 College will speak to Donna to discuss funding source; SL 102909 PO's have been placed waiting for install date from SPL; will follow up on the orders to see if two LCDs to replace the TVs.;SL 111009 equipment has been ordered; final walk through this afternoon. SL012210 waiting on doc cameras sched. for next Tues.
| Spring Break 2010 | New Request | 1 | Bio | S54 | N |  | Measure C |  | SL 111009 No MM at all; Janet to verify funds available; SL 012210 Req #: R653 - new full MM install; Console is in the room and has the infrastructure. Bill M. to verify the network port and Bill will put in a ticket to activate the network port. SL 022610 - PO will go out on Monday
| Spring Break 2010 | New Request | 1 | C Arts | A94 | N |  | Measure C | Busy fridays until 3? | Projection System; SL 112008 swapped with A92; SL 012210 full new system. REQ # R655SL 022610 PO went out a bit ago and on track for Spring Break install
| Spring Break 2010 |  | 1 | SS | L25 | N |  | Measure C | Fridays ok? | SL 112008 Swapped with G1; Sl 012210 Bill to get quote to Janet who will create PR within a week.SL 022610 Equip PO went out; Console PO has been delayed so at risk for Spring Break; Priority over G2 so when a console arrives it goes to this project
| Plug and play - as soon as it arrives. Spring Break | New Request |  | Bio | E32 | R |  | Measure C |  | SL 111009Needs a Doc camera; Bill M. sent spec of device to Javier; SL 012210 - PR submitted by Javier - Janet has not seen the PR - possible the wrong account code was entered. Lydia will get back to Javier or Jerry to find out who's queue its in. Janet only sees tecnology items if the account code is technology and Measure C purchases. SL 022610 PR Submitted? May be held up for wrong account.
| Spring Break 2010 | New Request |  | MiddleCollege | G1 and G2 |  | 2009-11-17 |  |  | Bill just finished installed a two project MM system in this double room. Janet said Middle College being moved into this area and the large double room being permanetly divided into two. Janet will determine if both rooms need MM. If so, then this needs to be prioritiezed. SL 012210 Was two rooms, then one room and now a new wall will create two rooms. Plant will build the wall - is there a pathway for voice/data? We need a project meeting w/ Donna and Lester to ensure the proper infrastructure is in the scope. Lydia said this is an instruction project and she needs to be involved in this and set the priority; SL 022610 When Frank builds wall - need to remove current MM out of the way. Move the console. During Break will install the MM system. Console may or may not be here in time.
| Spring Term 2010 |  |  | SS | L72 | R | 10/20/08 ETS | Measure C |  | (Elmo needs replace - DONE); SL 101608 ETS recommends a new projector - The college needs to prioritize this as a new request; SL 202610 still on track. SL 042310 Projector dying so PO was exepdited; moved from Summer to Spring.
| Spring Term 2010 |  |  |  | L24 | R | Nov 10 2009 | Measure C |  | ETS Initiated Repair: L24 – XG – C50X ( SHARP ) 06/04/03; Projector upgrade; SL 022610 Bill has the quotes - half day job and can be done on a Friday PM. Bill will ask Janet to order the projector. SL 042310 Was in here for summer term but really is planned for SPring term; PR is with Purch.
Summer Term 2010
| Summer Term 2010 |  |  |  | L84 | R | Nov 10 2009 |  |  | ETS Initiated Repair: L84 – XG – C50X ( SHARP ) 8/22/03; Projector upgrade; SL 022610 Bill will give quote to Janet to order.
| Summer Term 2010 | New Request |  |  | SC 2108 | R | Nov 10 2009 |  |  | ETS Initiated Repair: SC2108 – XG – C55X ( SHARP ) 8/14/04; Projector upgrade; Sl 042310 Jim & Bill Prioritize; Bill get Quotes
| Summer Term 2010 | New Request |  |  | SC 2210 | R | Nov 10 2009 |  |  | ETS Initiated Repair: SC2210 – XG – C55X ( SHARP ) 8/14/04; Projector upgrade; Sl 042310 Jim & Bill Prioritize; Bill get Quotes
| Spring Break 2010 / Spring Term | Spring Term 2010 |  | PSME | ? | ? |  | Prop 55 |  | SL 112008 Do not know the scope; SL 012809 Smart Boards/Mobile Carts/Fixed MM in the scope - Final decision is dependent on the cost of the furniture and computer equipment. Drop dead date for Jerry to have a decision is: Monday February 2.; SL 021709 Have scope and PRs in process; Sl 031809 - bought 3 LCD displays which need to be installed - On order to make the deadline to invoice by 5/15/09 need to have the install prioritized.; SL 052009 All equipment arrived. The self install equipment - tablets/mice etc. will give to Javier, the reminder Bill will develop a list to put into prioritization list for deployment; SL 060209 Equipment arrived, invoiceed and paid. Need to schedule the installation - need to get quotes and a account code for installation. Waiting on PSME. - Bill M. will contact Jerry R for an account code. SL 101009 All equipment arrived, but many pieces are in ETS storage and no funds to install the equipment: 3 Flat screens - all other equipment has been installed. College directed Bill M. to obtain quote for installation for the College to evaluate. There is also an overlay for one of the flat screens. SL 102909 Bill waiting for a site walk w/ Jerry and Javier and college needs to id the funding. SL 111009 Lydia still needs to speak to Jerry and Jerry needs to speak to Christina to obtain the funding for installation. Bill M. will do a walk through with Jerry and Javier today and obtain install quote from SPL; Letha has a non-measure C fund. SL 012210 Lydia: Jerry and Christina said they would get it taken care of. Lydia will speak to them again. SL 061110 Funding for install is available - Did Bill M. get a quote? | SL 022610 Letha said to arrange the install and Letha and Christina will identify the FOAP by March 5th. Then Bill and Janet will get the PR submitted
Summer Break 2010
N/A equipment already here | Anytime | New Request Jan 22, 2010 |  | Creative Arts | 12U Dance Studio |  |  |  |  | SL 012210 - The dept bought some equipment and they want it installed - Need to remove old equip, install new; About a days worth of work.; 042310 Equipment was installed - not what they wanted now want a CD player w/ iPod input w/ remote control - Bill gave the user (Warren) a quote not sure what happened to the order. Plug and play install
| Summer Term 2010 |  |  |  | G6 | R | Nov 10 2009 |  |  | ETS Initiated Repair: G6 – XG – C50X ( SHARP ) 6/1/02; Projector upgrade; SL 022610 Bill will give Janet the quote to order; SL 042310 Jim & Bill prioritize and then get quote
| Summer Break 2010 |  |  | App Tech | E 24 | N | Stephanie Sherman | Measure C |  | SL 111009 need to investigate the facilities readiness; SL 022610 - Had meeting w/ Plant and there may be trenching involved - met a long time ago. Lydia will speak to the Dean.; SL 042310 Stephanie wants this done; need to do a facilities readiness check; jose will represent the network team regarding the networking needs during the facilities readiness
| Summer Break 2010 or Winter Break 2010 |  |  |  | L48 | N | Nov 10 2009 | Measure C |  | ETS Initiated Repair: L48 – XG – C50X ( SHARP ) 04/09/003; Projector upgrade; SL 012210 Due to further investigation Bill and Jim said this system is old and does not have a control system and its on a cart. Would like to do a full system upgrade - may push back to summer 2010 - need to get buy in from Instruction side. 022610 Lydia will take back to Deans to prioritize since it still works and it will be considered a NEW install under Measure C; SL 042310 Will do a full upgrade - use the NEW Measure C MM budget 714
Fall Term 2010
| Summer Break 2010 |  |  | SS | L-27 | N |  | Measure C | Break Only | SL 112008 Swapped with G4; SL Bill will look for an opening in Spring Term available - pending Construction meeting on Monday 3/1; SL 042310 Bill get quote; Delayed due to console
| Summer Break 2010 | New Request |  | Middle College | G9 |  |  |  |  | SL 042310 Was supposed to be done around the time as G2 per Donna JD; Using a temp MM system now want something permanent. Lydia speak to Donna about how to prioritize this. 092410 Waiting on Console
| Summer Break 2010 |  |  | SS | L-28 | N |  | Measure C | Busy fridays until 12 | SL 112008 Swapped with G4; SL Bill will look for an opening in Spring Term available - pending Construction meeting on Monday 3/1; SL 042310 Bill get quote; Delayed due to Console.
| Summer Break 2010 / Winter Break 2010 | New Request |  | Nancy Canter/ Creative Arts | G3 | N | Nov 10 2009 |  |  | SL 111009 need to investigate the facilities readiness. Theater type room; 042310 Bill M. work w/ Nancy to determine scope; 081710Bumped to Winter Break 2010 due to lighting which requires a special projector. 092410 have pricing in hand today
| Fall Term 2010 |  |  | IIS | MCC-116 | R |  | Measure C |  | SL 021709 Protect during renovation- Refreshed equipmemnt; sepctrum cart
| Fall Term 2010 |  |  | IIS | MCC-117 | N |  | Measure C |  | SL 021709 Protect during renovation;refreshed equipment; Spectrumcart
| Fall Term 2010 |  |  | IIS | MCC-115 | N |  | Measure C |  | Activity Area - new equipment; Spectrum card
| Fall Term 2010 |  |  | IIS | MCC-118 | N |  | Measure C |  | Conf room/seminar; Spectrum Cart
| Fall Term 2010 |  |  | IIS | MCC-119 | N |  | Measure C |  | classroom
| Fall Term 2010 |  |  | IIS | MCC-120 | N |  |  |  | Classroom
Winter Break 2010
| Fall Term 2010 |  |  | SEMINAR | OTI/Conf/training 107 | N |  |  | Fall/December 09 INSTALL WINTER TERM 10 in use | Spectrum Cart
| Fall Term 2010 |  |  | SEMINAR | Classroom ROOM 118 | N |  |  | Fall/December 09 INSTALL WINTER TERM 10 in use | fixed console full system
| Winter Break 2010 | New Request Feb 26, 2010 |  | BIoHS | S73 | N | 022610 Stephanie Sherman | Measure C |  | Need a new projector; does not have a control system so this is not a refresh, but NEW since it really was not a full MM system installed originally
New Request 092410 |  |  | ? | CIS | AT 202 | N | Fall Term | Measure C |  | Want a visualizer/document camera. Need to evaluate the room set up and infrastructure. May need infrastructure work.
| Winter Break 2010 | New Request |  | PSME | G5 |  |  | Measure C |  | ?
| Summer Term 2010;changed to Winter Break 2010 | New Request |  |  | ATC 313 | R | Nov 10 2009 |  |  | ETS Initiated Repair: ATC 313 – PT – L711U ( PANASONIC ) 07/01/01; Projector upgrade; Jim & Bill Prioritize; Bill get Quotes; 081710 Delayed because the user wants specialized project - wide aspect projector - Winter Break 2010; Sl 092410 can use a Friday to do the work
New Request 092410 | Winter Break 2010 | New Request |  |  | ADM106 | Repair? |  |  |  | Projector has a problem - may still under warranty
New request 092410 | Winter Break 2010 | New Request |  |  | G7 | R |  |  |  | Projector has a problem.
| Winter Break 2010 | New Request |  |  | E25 |  |  | Measure C |  | ?
Winter Term 2011
[5 empty] | ATC205 | New |  | MC |  | Doc camera only
| Winter Term 2011 |  |  |  | ATC204 | New |  | MC |  | Doc camera only - waiting for rest of bldg renovation
Spring Break 2011
| Spring Break | New Request 020411 - Bill found out thru Lester Lyons; Janet doesn't know anything about it. | Projector/speakers- want to add a small lecturn w/ a computer and DVD/VCR - will be installed at a later time |  | LC138 | New |  | Donna? |  | Space is to be renovated inhouse? Now being rented out by PA University; recommend a new projector and no reason to pay install fees for an old used projector