## Assignments
Standard |  | Planning Agenda | Group Assignment | Contact | Progress | Evidence/Date to be Completed
I.A.3 | As a component of the new planning process, the mission statement will be publicized |  | College Council | Brian and Mayra | Completed | Spring 2010
| on a regular basis. The review of the mission statement will be integrated into |  |  |  |  | www.deanza.edu/ir/planning/
| the planning process. |  |  |  |  | http://www.deanza.edu/ir/planning/Quilt_Chart_11_14_13_Detail_approved.pdf
I.B.1 | The college will implement the integrated planning process that incorporates |  | College Council | Brian and Mayra | Complete | www.deanza.edu/ir/planning/
outcomes assessment results into institutional planning, and provide the
time and space for broad- based dialogue aimed at improving student learning.
I.B.3 | The college will implement the integrated planning process that incorporates |  | College Council | Brian and Mayra | Ongoing | www.deanza.edu/ir/planning/
| outcomes assessment results into institutional planning, and student learning provide |  | SLO Steering
the time and space for broad-based dialogue aimed at improving student learning.
II.A.1 | Working with other Planning and Budgeting Teams and College Council, the Instructional |  | College Council | Brian and Mayra | Ongoing | http://deanza.edu/gov/SSPBT/notes/
| Planning and Budget Team (IPBT) will review and modify the Annual Program |  | PBTs | Letha + Margaret, Christina + Randy, Stacy + Kevin |  | http://www.deanza.edu/gov/IPBT/resources.html
| Review Update and Comprehensive Program Review processes on a regular basis. |  | Academic Senate | Mayra and Randy |  | ongoing and documented on IPBT website; linked on Senate website
II.A.1.b | Develop a Distance Learning course student evaluation, based on the Foothill-De Anza Faculty Agreement Article 6 and Appendix J2W. |  | Academic Senate | Mayra and Randy | Ongoing | The student evaluation for OL instruction was signed off in the spring of 02. It was not implemented until the fall of 12 and only at FH due to technical and financial limitations. I am placing the minutes of the discussions between FA and the District regarding the implementation of the OL student evaluation in your De Anza mailbox. | See next tab for specifics
|  |  | & FA & Learning Resources | Rich & Lisa
II.A.1.b | Develop faculty training on effective online teaching strategies to improve |  | Academic Services | Rowena | in progress | Learning Resources
student success and retention.
II.A.1.c | Institutional Research will continue its commitment to assisting faculty and staff in their |  | College Council | Brian and Mayra | Ongoing | www.deanza.edu/ir
| assessment efforts at the course and program levels. |  |  |  |  | http://www.deanza.edu/ir/program-review.html | Continued development of intrgrating the AUO s into the Comprehensive program reviews. Used the updated format for the comprehensive program reviews done this year. Discussed assessment tools for AUO outcomes. http://www.deanza.edu/gov/ERCOPBT/notes
II.A.1.c | The Planning and Budget Teams will reflect on and enhance Program Review processes and criteria to more fully develop effective assessment methods for Student Learning Outcomes Assessment Cycle and Program Level Outcome Assessment Cycle results. |  | PBTs | Letha + Margaret, Christina + Randy, Stacy + Kevin | Ongoging | http://deanza.edu/gov/SSPBT/notes/
|  |  | & SLO Steering | Mary & Tono |  | http://www.deanza.edu/gov/IPBT/resources.html
http://deanza.edu/gov/SSPBT/notes/
II.A.2.a | The SLO team will continue to refine its processes to assist faculty in efficiently and effectively documenting and assessing Student Learning Outcomes. |  | SLO Steering | Mary & Tono | Ongoing | http://deanza.edu/slo/2012_SLO_Survey.pdf; 2013 SLO Convocation April 27, 2013: http://www.deanza.edu/gov/academicsenate/notes/Draft%20Notes%20of%20%20January%2014th.docx
http://deanza.edu/slo/2012_SLO_Survey_Results.pdf; Help Shops: http://deanza.edu/slo/minutes/2012_October_SLO_Team_Minutes.pdf
II.A.2.a | The college will continue to encourage professional growth in the area of assessment through the Office of Staff and Organizational Development. Staff Development activities related to the development, interpretation and analysis of course and program assessments will continue. |  | SLO Steering | Mary & Tono | Ongoing | http://prezi.com/slzognwzvjhm/de-anza-partners-in-learning-2012/?auth_key=88bb1b8dd755ed6ad39a3161cd67a480c4725d95
http://www.deanza.edu/president/OpeningDay2010.pdf
http://www.deanza.edu/president/SSLOworkshop091710.pdf
http://www.deanza.edu/staffdev/orientation/septorientation.html
II.A.2.a | Complete assessment of Program Level Outcomes by the end of 2013-14 academic year. |  | SLO Steering | Mary & Tono | Spring 2014 | http://deanza.edu/slo/newsletters/NwsLter_September_2012.pdf
II.A.2.a | Workshops will be conducted in order to introduce PLOACs. |  | SLO Steering | Mary & Tono | November 2010, January 2011 | http://www.deanza.edu/slo/Assessing%20Program-Level%20SLOs.pdf
II.A.2.b | Develop an assessment plan for Program Level Outcomes. |  | SLO Steering | Mary & Tono | Winter 2011 | http://deanza.edu/slo/Assessing%20Program-Level%20SLOs.pdf
II.A.2.b | The Academic Senate, through the SLO Steering Committee and team, will continue |  | SLO Steering |  | Ongoing | http://deanza.edu/slo/accjc_evidence/AS_Notes_November_29th.pdf
| to encourage faculty to develop reasonable program level assessment techniques. |  |  | Mary & Tono |  | http://deanza.edu/slo/accjc_evidence/AS_notes_January%2031st%20_2011_.pdf
II.A.2.b | The SLO Steering Committee will continue to refine SLOACs in all areas of the college in order to achieve meaningful use of data into practice. |  | SLO Steering | Mary & Tono | 2011-03-01 | http://deanza.edu/slo/revisionMarch2011_Liaison_Workshop.pdf
[5 empty] | 2011-04-01 | http://deanza.edu/slo/2011_Convocation_Summary.pptx
[5 empty] | 2012-04-01 | http://deanza.edu/slo/newsletters/SLO_Convocation_Flyer_2012.pdf
[5 empty] | 2012-06-01 | http://www.deanza.edu/slo/newsletters/NwsLter_June_2012.pdf
[5 empty] | 2012-12-01 | http://deanza.edu/slo/newsletters/NwsLter_September_2012.pdf
[5 empty] | 2012-12-01 | http://deanza.edu/slo/newsletters/NwsLter_December_2012.pdf
II.A.2.d | Develop a centralized technology training plan that addresses faculty training. |  | Tech Taskforce | Letha + Kevin | No
II.A.2.d | Develop additional faculty training for Distance Education. |  | Academic Services | Rowena | Complete | We have done this but will continue to add more. We have facilitated Effective Practice Showcase every quarter. We have hosted webinars and sponsored faculty in other professional development conferences including the Online Teaching Conference. Technology Supported Learning and Retention workshop: Feb. 4, 2011 & June 7, 2011; Effective Practices Showcase: Nov. 16, 2011,Feb. 24, 2012, May 22, 2012, Nov. 7, 2012
II.A.2.d | Increase staff development in the institutional Strategic Initiatives: Outreach |  | Academic Services | Rowena | In Progress | Academic Services
| Student Retention and Success, Cultural Competence, and Community Collaborations. |  |  |  |  | evidence from staff development ,equity office, and Developmental and Readiness ERDucation Taskforce
II.A.2.g | Create an inventory of areas that have departmental exit exams and |  | SLO Steering | Mary & Tono | Ongoing | Nursing PLOAC Work on TracDat evidences progress
encourage appropriate alignment with SLO assessments.
II.A.2.i | Faculty will develop and conduct a comprehensive approach to |  | SLO Steering | Mary & Tono | 2012-04-27 | http://deanza.edu/slo/accjc_evidence/SLO_Convocation_Flyer_2012.pd
| meaningful assessment of certificate and degree programs. |  |  |  | 2011-04-15 | http://deanza.edu/slo/accjc_evidence/2011_SLO_Convocation_Manual.pdf
II.A.3.a | Develop a plan to assess General Education outcomes. |  | Curric/Acad Sen. | Anu, Mayra, Randy | Complete | 2009; documented on Academic Senate & Curriculum websites | See Additional Documents in folder.
II.A.3.a | Implement revised GE Philosophy and Area Descriptors for inclusion in 2013-2014 catalog. |  | Curric/Acad Sen. | Anu, Mayra, Randy | Complete | Spring 2013; documented on Academic Senate website | See Additional Documents in folder.
II.A.3.c | Assess student achievement of the GE outcomes and Institutional Core Competencies. |  | Curric/Acad Sen. | Anu, Mayra, Randy | Ongoing | 1st ICC/GE assessment 2012; progress documented on Senate & SLO websites | See Additional Documents in folder.
II.A.6 | Divisions will periodically review syllabi for consistency with appropriate |  | Office of Instruction | Christina | No
standards, including content, methods and college policies.
II.A.6.b | Working with Foothill College, draft a joint policy on program discontinuance for discussion at both colleges. |  | Academic and Professional Mat's | Paula Norsel | Complete | The program discontinuance policy was discussed and approved at the 2/24/12 Chancellor's Advisory Council meeting and the administrative procedure at the 4/13/12 meeting. Finally, the 3/5/12 and 3/12/12 Board of Trustees meeting minutes reflect discussion and approval of the program discontinuance policy. See email from Paula Norsel on 3/7/13
II.A.6.b | Assess effect of elimination of Readiness co-requisites on student success |  | Academic Services | Rowena | In Progress | Learning Resources
and retention in developmental and freshman transfer-level English.
II.A.6.c | Continue to evaluate the effectiveness of the overall college website through student focus groups and faculty and staff input. |  | Marketing | Marisa | In Progress | Summer 2013 | Conduct a survey and focus group in fall 2014
II.A.6.c | Continue to improve and enhance the online searchable schedule of classes. |  | Marketing | Marisa | In Progress | Summer 2013 | Conduct a survey and focus group in fall 2014
II.A.7.b | Improve Student Development-related websites in the content and |  | Student | Marisa and Michele | Completed | Student Handbook: http://www.deanza.edu/studenthandbook/
| presentation of information, including as it relates to academic honesty. |  | Devel't & Marktng |  | 2013-03-08 | Student Development: http://www.deanza.edu/studentdevelopment/
II.A.7.b | Revamp the Student Handbook for content and presentation and increase visibility of the handbook on the college website. |  | Student Devel't & Marktng | Marisa and Michele | Completed 3/8/2013 | Academic Integrity: http://www.deanza.edu/studenthandbook/academic-integrity.html and http://www.deanza.edu/studentdevelopment/studentjudicialaffairs.html
II.B.3.c | With the leadership of the Vice President of Student Services, the Dean of Counseling and Matriculation, and the Counseling Department Chair, Counseling and Advising will evaluate through surveys, focus groups and ongoing discussions how to improve services. |  | SSPBT | Stacy and Kevin | Ongoing | Accreditation_counseling%20planning%20agendas-1.docx
http://deanza.edu/ir/deanza-research-projects
II.B.3.d | With the leadership of the Associate Vice President of Instruction, the college will hire a director for the redefined Office of Equity, Social Justice and Multicultural Education. |  | Academic Services | Rowena | In Progress | Academic Services Spring 2012
II.B.3.d | With the leadership of the AVPI, the Director of ICCE, the Director of Equity, Social Justice and |  | Academic Services | Rowena | in progress | Academic Services
| and Multicultural Education, and the Director of Staff and Organizational Development, |  |  |  |  | planning meetings be held
| will collaborate with DASB to establish updated strategic plans focused on |  |  |  |  | project focus on leadership development
student access and engagement for their departments.
II.B.3.e | Assessment, in conjunction with the DARE Task Force, will determine, |  | DARE Taskforce | Mayra and Lorrie | Complete | Determine & prioritize:Completed December 2011
| prioritize and implement best practices to improve Assessment Center services to |  | Assessment | Stephen |  | Implementation: Assessment website updated &
| students including in the placement of students in developmental education courses. |  |  |  |  | Test Prep Boot Camp & Math Modules completed, Winter 2011; The completion date was 4/1/13 when the Assessment Center implemented the multiple measure items into the Accuplacer assessment process.
II.B.3.e | The dean of Counseling and Matriculation will work with the |  | SSPBT | Stacy and Kevin | Oct. 2011 | Accreditation_counseling%20planning%20agendas-1.docx
Matriculation coordinator to establish a Matriculation Advisory Board.
II.B.4 | The SSPBT will continue to refine Student Services Learning Outcomes Assessment |  | SSPBT | Stacy + Kevin | Ongoing | http://deanza.edu/gov/SSPBT/notes/
| Cycles to assist in planning, program evaluation and decision-making. |  | SLO Steering | Mary & Tono
II.B.4 | Working with other PBTs and College Council, SSPBT will review and modify the Annual |  | SSPBT | Stacy + Kevin | Ongoing | http://deanza.edu/gov/SSPBT/notes/
Program Review Update and Comprehensive Program Review processes regularly.
II.B.4 | Develop an assessment plan for Program Level Outcomes. |  | SLO Steering | Mary & Tono | Ongoing | http://deanza.edu/slo/minutes/index.html
II.C.1 | Facilitate an increase in fully online, partially online and hybrid course offerings through Distance Learning instructional design and training assistance. |  | Learning Resources and Curriculum | Lorrie, Anu | Ongoing | Background is that we would like to offer more training but there need to be more incentive and support for faculty to participate.Yes we have done this but will continue to look for ways to do this more effectively. We offered the Technology Supported Learning & Retention workshop twice, can continue if needed. Only a very few faculty member attended. We didn't do it as an ongoing event because of the low turnout, and also since the facilitator moved out of the area.
II.C.1 | With leadership of the Learning Resources dean, engage more faculty in the integration |  | Learning Resources | Lorrie, Anu | Underway | Library redesign is under way. Planning agenda will be met with redesigned space.
| of Library services, including orientations as part of courses and Learning Communities. |  | & Curriculum
II.C.1 | Redesign Library space or create larger instructional lab to accommodate more students. |  | Learning Resources | Lorrie | No
II.C.1 | Redesign circulation and reference/instruction desk areas to improve service. |  | Learning Resources | Lorrie | No
II.C.1.b | Explore creative ways to utilize existing faculty and technologies to fully |  | Academic Services | Rowena, Lorrie | in progress | meetings held with General Education Committee
| develop an enhanced information literacy program. |  | Learning Resources |  |  | Learning Resources, Discussion has started but needs to be accelerated.
III.A.1.d | Explore additional ways to educate employees about different working |  | Academic Services | Rowena | in progress | Academic Services
| styles and interpersonal work relationships. |  |  |  |  | evidence from staff development and equity office
III.A.2 | With the oversight of College Council and College Planning Committee, continue to ensure Educational Master Plan goals and integrated planning drive staffing decisions. |  | College Council | Brian and Mayra | Ongoing | http://www.deanza.edu/ir/state-of-the-college-related-information/index.html | Faculty hire requests are ratified by College Council and are aligned with program data and institutional goals.
www.deanza.edu/ir/planning/
III.A.3.a | With the leadership of the AVPI, the college will hire a director for the redefined |  | Academic Services | Rowena | Yes | Academic Services: Spring 2012
& III.A.4 | Office of Equity, Social Justice and Multicultural Education.
III.A.4 | With the leadership of the associate vice president of Instruction, the director of ICCE, |  | Academic Services | Rowena | in progress | Academic Services
| the director of Equity, Social Justice and Multicultural Education, and the director of |  |  |  |  | planning meetings held
| Staff and Organizational Development will collaborate with the De Anza Associated |  |  |  |  | project focus on leadership development
Student Body to establish updated plans focused on student access and engagement.
III.A.4.a | Explore opportunities to increase funding for diversity programs on campus. |  | Academic Services | Rowena | In Progress | Spring 2013 and Ongoing External Grants, Academic Services | Academic Services; in progress--prioritization planning meetings, collaboration with external grants
III.A.5 | Work toward a centralized technology training plan, based on wide-ranging input from |  | Tech Taskforce | Letha + Kevin | No
faculty, staff and students, as well as all staff involved in delivering training, both at the
campus and district level. The plan should address the questions of how training needs
are assessed and how training will be assessed and evaluated, in addition to guiding
users toward the appropriate location to receive the training.
III.A.5.a | Explore opportunities to maximize staff development during constrained budget times. |  | Academic Services | Rowena | In Progress | Academic Services; in progress--prioritization planning meetings, collaboration with external grants
III.A.6 | Increase communication throughout shared governance about the integration of human resources planning with institutional planning. |  | College Council | Brian and Mayra | Complete | Increased communication through the three PBT and College Council. All decisions are brought to College Council for approval (centralized approach). Budget allocations are shared with shared governance groups. All PBT affirm that resource planning is aligned with institutional planning.
III.B.1.a | Complete the update of the Facilities Master Plan. |  | Educational Res. | Donna | Yes | November 8, 2012: http://www.deanza.edu/gov/campus_facilities/pdf/DAC_FacilitiesMasterPlan2011_16.pdf
III.B.2.b | Complete the update of the Facilities Master Plan. |  | Educational Res. | Donna | Yes | November 8, 2012: http://www.deanza.edu/gov/campus_facilities/pdf/DAC_FacilitiesMasterPlan2011_16.pdf
III.C.1.b | Work toward a centralized technology training plan, based on wide-ranging input from |  | Tech Task Force | Letha + Kevin | No
faculty, staff and students, as well as all staff involved in delivering training, both at the
campus and district level. The plan should address the questions of how training needs
are assessed and how training will be assessed and evaluated, in addition to guiding
users toward the appropriate location to receive the training.
III.C.1.d | Continue to integrate the Information Technology Strategic Plan into |  | Tech Taskforce | Letha + Kevin | No
campus planning and budgeting initiatives.
III.D.1.b | Develop clear policies and processes for writing and pursuing grants. |  | Budget Committee | Letha and Mayra | No
III.D.1.d | Working with other Planning and Budget Teams and College Council, the Finance and |  | FERPBT | Letha and ? | Ongoing | http://deanza.edu/gov/SSPBT/notes/ | There is collaboration between all PBTs on a regular basis.
| Educational Resources Planning and Budget Team will review and modify the Annual |  |  |  |  | http://www.deanza.edu/gov/IPBT/resources.html
Program Review Update and Comprehensive Program Review processes regularly.
IV.A | Continue review of governance and decision-making models. |  | College Council | Brian and Mayra | Complete - Spring 2014 | www.deanza.edu/ir/planning/; http://deanza.edu/gov/SSPBT/notes/ | College Council ratifies the Haynes, the QUILT. The latest revision includes 14-15 as a year of reflection.
IV.A.1 | Encourage faculty, staff and administrators to improve communication by |  | College Council | Brian and Mayra | Complete - Spring 2014 | District wide OMNI update in progress as a license has been obtained to begin the process to migrate and improve faculty websites and provide website access for all faculty wishing to develop their website.
maintaining and updating websites.
IV.A.2 | Improve understanding of shared governance process by standardizing the governance |  | College Council | Brian and Mayra | Complete | http://www.deanza.edu/gov/gov_eHandbook_rev3-31.pdf
website in presenting roles, charges and responsibilities of shared governance groups.
IV.A.2.a | Explore release time and/or stipends for classified professional participation |  | College Council | Brian and Mayra | Ongoing | Administrative team has explored release/stipends with district HR. College Council will be exploring ways for wider participation of classified professionals to participate in shared governance.
in leadership roles as a way of encouraging widespread participation in governance.
IV.A.5 | Produce a governance e-Handbook describing governance groups and |  | College Council | Brian and Mayra | Complete | http://www.deanza.edu/gov/gov_eHandbook_rev3-31.pdf
| decision-making processes in a standardized online format. |  |  |  |  | Governance handbook was completed in 2012 and is reviewed annually by the CPC.
IV.B.1.a | Work with the Chancellor’s office to increase the understanding and |  | College Council | Brian and Mayra | Complete | The Board of Trusteees evaluation reflected the need for campsus visibility and know how to advocate. Trustees report at every Board meeting on advocacy activities. Board Trustees mentor Student Trustees to support their understanding of disctrict and college matters.
awareness of the campus community about trustee and district advocacy activities.
IV.B.2.d | Increase awareness and implementation of the 6-Year Planning and Assessment Cycle approved and in the Ed. Master Plan as it relates to budget and resource allocation. |  | College Council | Brian and Mayra | Complete | http://www.deanza.edu/ir/state-of-the-college-related-information/index.html | Reviewed and updated cycle. There is a closer alignment of resource allocation and program planning including the utlization of Measure C funds.
www.deanza.edu/ir/planning/; http://deanza.edu/gov/SSPBT/notes/